## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login | Admin username field was case sensitive | Low | 1 | 9 | Use the planned debugging time
2 | 1 | Student add bid, drop bid | Variable not found error when student access BIOS before admin conducts bootstrap | Low | 1
3 | 1 | Sidebar navigation | Token wasn't passed when navigating through sidebar | Low | 1
4 | 1 | Student add bid, drop bid | Submit button didn't pass token, causing student to get logged out after submitting | Low | 1
5 | 1 | Bootstrap | Temporary files were left undeleted in temp folder | Low | 1
6 | 1 | Bootstrap | The argument '0' was taken in as an empty field | Low | 1
7 | 1 | Bootstrap | There is no validation for amount when it takes in non numeric values | Low | 1
8 | 1 | Bootstrap | Maximum number of characters for userid was mistaken to be 128 instead of 100 | Low | 1
9 | 1 | Bootstrap | Validation for description was slightly wrong (e.g. if(strlen($description > 1000)) ) where strlen($description > 1000) means strlen(true). | Low | 1

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login | Admin username field was case sensitive | Unresolved | 2019-09-27 | 2019-10-01 | Amey / Rouhui
2 | 1 | Student add bid, drop bid | Variable not found error when student access BIOS before admin conducts bootstrap | Resolved | 2019-09-27 | 2019-09-29 | Brian / Ian
3 | 1 | Sidebar navigation | Token wasn't passed when navigating through sidebar | Resolved | 2019-09-26 | 2019-09-26 | Brian / Ian
4 | 1 | Student add bid, drop bid | Submit button didn't pass token, causing student to get logged out after submitting | Resolved | 2019-09-29 | 2019-09-29 | Brian / Ian
5 | 1 | Bootstrap | Temporary files were left undeleted in temp folder | Resolved | 2019-09-29 | 2019-09-29 | Gordon
6 | 1 | Bootstrap | The argument '0' was taken in as an empty field | Resolved | 2019-09-29 | 2019-09-29 | Gordon
7 | 1 | Bootstrap | There is no validation for amount when it takes in non numeric values | Resolved | 2019-09-29 | 2019-09-29 | Gordon
8 | 1 | Bootstrap | Maximum number of characters for userid was mistaken to be 128 instead of 100 | Resolved | 2019-09-29 | 2019-09-29 | Gordon
9 | 1 | Bootstrap | Validation for description was slightly wrong (e.g. if(strlen($description > 1000)) ) where strlen($description > 1000) means strlen(true). | Resolved | 2019-09-29 | 2019-09-29 | Gordon
10 | 2 | Bootstrap and Add bid | Perform bootstrapping which includes a bid from zac.ng(SOB student) for IS100 (IS course) | Resolved | 2019-10-08 | 2019-10-08 | Ian/Brian
11 | 2 | Minimum e$10 for bidding | Bids less than e$10 were successful | Resolved | 2019-10-08 | 2019-10-08 | Ian/Brian
12 | 2 | Error numbering | When 2 errors were discovered ( Minimum bid cannot be less than e$10, you have already completed this ourse), the error numbering for both were 1 | Resolved | 2019-10-08

## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.