## Slide 1: Final Presentation (G3-T4)
Prepared By: Gordon, Amey, Brian, Rou Hui, Ian

## Slide 2: Agenda
Schedule
Bug Metric
Use of Git
Key Takeaways & Challenges Faced

## Slide 3: Schedule

## Slide 4: Actual vs Planned
Week 5
Week 6
Week 7
Week 8
Week 9
Interim Review Presentation
2 Oct
Status Review
16 Oct
Iteration 1
Task | Planned | Actual
Iter 1 Planning | 19/9 - 19/9 | As planned
Database structure | 20/9 - 20/9 | 19/9 - 19/9
Student login process, CSS design | 20/9 - 20/9 | As planned
Remaining DAOs, common files, bootstrap | 21/9 - 24/9 | 23/9 - 26/9
Integrate, Test, Debug, Deploy | 26/9 - 30/9 | 27/9 - 1/10
Student bidding, Round 1 clearing | 28/9 - 30/9 | 29/9 - 10/1
Iteration 2
Task | Planned | Actual
Iter 2 Planning | 3/10 - 3/10 | 2/10 - 2/10
Code round 2, integrate code | 4/10 - 7/10 | As planned
Testing | 9/10 - 11/10 | 10/10 - 15/10
Deploy, test & debug | 12/10 - 13/10 | 13/10 - 15/10
Iter 2 milestone prep | 14/10 - 14/10 | 15/10 - 15/10

## Slide 5
Week 9
Week 10
Week 11
Week 12
Week 13
Iteration 3
Task | Planned | Actual
Iter 3 Planning | 17/10 - 17/10 | 16/10 - 16/10
Code timetable, search bid | 17/10 - 19/10 | 19/10 - 29/10
Integrate code | 19/10 - 20/10 | 29/10 - 29/10
Test code (JSON, bug metrics) | 17/10 - 26/10 | 30/10 - 30/10
Deploy to AWS, test | 27/10 - 27/10 | 29/10 - 29/10
Milestone preparation | 29/10 - 29/10 | As planned
Iteration 4
Task | Planned | Actual
UAT debugging | 31/10 - 6/11 | As planned
Final submission preparation | 31/10 - 11/11 | As Planned
Week 14
Iteration 5
Task | Planned | Actual
Final Submission review | 13/11 - 16/11 | As Planned
Code bid status JSON | Unplanned | 16/11
Final testing & debugging of front-end & JSON | Unplanned | 17/11
Final submission | 17/11 | As Planned
Final presentation preparation | 14/11 - 17/11 | As Planned
Final presentation | 18/11 | As planned
UAT
30 Oct
Final Presentation
20 Nov
Final Submission
17 Nov

## Slide 6: Adding Functionalities & PHP Frameworks
Additional Functionalities Implemented:
Student’s timetable
Searching for classes
PHP Frameworks / External libraries were NOT used because:
Web application required isn’t too complex
Team’s lack of experience in this aspect

## Slide 7: Breakdown of Work
Iteration 1 | 
Programming | Non-Programming
Code student login process – Amey & Rou Hui | Iteration 1: Planning – All Members
Basic CSS design – Brian & Ian | Design database structure – Brian & Ian
Code remaining DAOs – Brian & Ian | Test code – All Members
Code Common files – Amey & Rou Hui | Iteration 1: 2nd meeting (Plan round 1) – All members
Code bootstrap – Brian & Ian | Iteration 1: 3rd meeting (PM review prep) – All members
Integrate code – Amey & Rou Hui | Deploy to AWS – Brian & Ian
Debug code – Brian & Ian | 
Student bidding (add, drop) – Amey & Rou Hui | 
Student bidding (view results) – Brian & Ian | 
Round 1: Clearing Logic – Brian & Ian | 

## Slide 8: Breakdown of Work
Iteration 2 | 
Programming | Non-Programming
Round 2 View Real Time Bids – Gordon & Ian | Iteration 2: Planning – All members
Round 2 Clearing Logic and View Results – Brian & Rou Hui | Deploy code to AWS – Gordon & Ian
Integrate code – Gordon & Ian | Test code – All members
Debug code – Brian & Rou Hui | Online Review Preparation – All members

## Slide 9: Breakdown of Work
Iteration 3 | 
Non-Programming | Programming
Code timetable – Gordon & Rouhui | Iteration 3: Planning – All members
Code search bid – Amey & Brian | Iteration 3 Second meeting – All members
Integrate code – Gordon & Rouhui | Deploy to AWS – Gordon & Rouhui
Debug code – Amey & Brian | Test code – All members
UI Design– Amey & Brian | 

## Slide 10: Breakdown of Work
Iteration 4 | 
Programming | Non-Programming
UAT Debugging - Amey & Brian | Preparation - Schedule – All members
 | Preparation - Bug Metric – All members
 | Preparation - Use of GIT – All members
 | Preparation - Others – All members
Iteration 5 | 
Programming | Non-Programming
Code bid status JSON - Amey & Brian | Final Presentation Preparation – All members
Final testing and debugging of front-end & JSON - Amey & Brian | Final Presentation – All members

## Slide 11: Work Allocation
 | Amey (AR) | Brian (BG) | Gordon (GL) | Ian (IL) | Rou Hui (RH)
Programming Hours | 53.5 | 55 | 59.5 | 54.5 | 53.5
Non-Programming Hours | 109.5 | 105 | 97 | 104.5 | 108.5

## Slide 12: Fair Distribution of Hours
Deviation from the Average Programming Hours |  | 
 | Highest | Lowest
Programming Hours | 7.79% | 3.08%
Non-Programming Hours | 4.39% | 7.53%

## Slide 13: Challenges in Tracking the Schedule
Inexperienced with estimating duration of project tasks
Tendency to under/over-estimate the amount of time required
But accuracy of estimation increased over the course of the project
Managing changes (in requirements, tasks, etc)
Initial schedule needed to be adjusted accordingly
Team meeting was necessary to ensure goals are aligned and changes are being kept abreast of
Ensuring consistently fair distribution of allocated hours
Requires coordination & effort from the team to ensure the <10% deviation from average programming hours rule is adhered to

## Slide 14: Bug Metrics

## Slide 15: Bug Log – Iteration 1
Function | Description | Severity | Points
Login | Admin username field was case sensitive | Low | 1
Student add bid, drop bid | Variable not found error when student access BIOS before admin conducts bootstrap | Low | 1
Sidebar navigation | Token wasn't passed when navigating through sidebar | Low | 1
Student add bid, drop bid | Submit button didn't pass token, causing student to get logged out after submitting | Low | 1
Bootstrap | Temporary files were left un-deleted in temp folder | Low | 1
Bootstrap | The argument '0' was taken in as an empty field - Resolved | Low | 1
Bootstrap | There is no validation for amount when it takes in non numeric values | Low | 1
Bootstrap | Maximum number of characters for userid was mistaken to be 128 instead of 100 | Low | 1
Bootstrap | Validation for description was slightly wrong (e.g. if(strlen($description > 1000)) ) where strlen($description > 1000) means strlen(true). | Low | 1

## Slide 16
Mitigation: Use the planned debugging time in the iteration
Final Value of Bug Metric for Iteration 1
9

## Slide 17: Bug Log – Iteration 2
Function | Description | Severity | Points
Bootstrap | Perform bootstrapping which includes a bid from zac.ng(SOB student) for IS100 (IS course) | High | 5
Minimum e$10 | Bids less than e$10 were successful | High | 5
Error checking | When 2 errors were discovered ( Minimum bid cannot be less than e$10, you have already completed this course), the error numbering for both were 1 | Low | 1
Error checking | When section and bid amount are left empty, no errors are shown | Low | 1
Drop section | Error pops up when section is dropped!! Section has been dropped successfully but e$ has not been refunded | Low | 1
Round 2 clearing | 2 students bid the same amount for one vacancy, both are suppose to fail. An error is thrown when round 2 is closed | Low | 1

## Slide 18
Mitigation: Bugs found were debugged immediately,
no extra time is needed
Final Value of Bug Metric for Iteration 2
14

## Slide 19: Bug Log – Iteration 3
Function | Description | Severity | Points
Timetable | Bid added through bootstrapping does not show up on timetable | Low | 1
Bootstrap | Bootstrap did not clear round 2 bid table | High | 5
Drop Section | Round 1.5 (after Round 1 ends, before Round 2 starts) allowed student to drop section | Low | 1
Round 2 clearing | Neither successful nor unsuccessful tables are updated after Round 2 closes | High | 5
Bootstrap JSON | File specific validations for a row even if common validations failed | Low | 1
Bootstrap JSON | Some checks added error message to $errors instead of individual row error array | Low | 1
Dump Table JSON | Keys were 'courses' and 'students' instead of 'course' and 'student' | Low | 1
Update Bid JSON | Other logical validations are checked even if 'round ended' check fails | Low | 1
Update Bid JSON | Section limit of 5 did not include both round 1 successful sections + round 2 bids | Low | 1
Delete Bid JSON | Student did not get refunded e-$ due to calling of wrong function | Low | 1
Delete Bid JSON | No such bid' check was done even if course / user / section round checks failed | Low | 1
Update Bid JSON | Timetable clash check does not check for successful sections when run during Round 2 | Low | 1

## Slide 20
Mitigation: Bugs found were debugged immediately,
no extra time is needed
Final Value of Bug Metric for Iteration 3
20

## Slide 21: Bug Log – Iteration 4
Function | Description | Severity | Points
Real time bid | Real time vacancies reflected the actual number of bids, instead of showing vacancies from round 1 (from UAT) | High | 5
Bootstrap | Updating bid was not processed properly (from UAT) | High | 5
Bootstrap JSON | Bid could not be checked and updated because the specific course section bid was used instead of only checking for course | High | 5
Round 1 Clearing | Round 1 clearing did not process properly for a section with 1 vacancy | Low | 1
Update Bid JSON | Did not check in the event when a student did not bid for a course for round 2 | Low | 1
Update Bid JSON | Did not re-calculate minimum bid after every successful bid in round 2 | Low | 1
Mitigation: Bugs found were debugged immediately,
no extra time is needed
Final Value of Bug Metric for Iteration 4
18

## Slide 22: Bug Log – Iteration 5
Function | Description | Severity | Points
Real time bid | After a student bids during round 2, real time bid is only updated upon page refresh | Low | 1
Round 2 Bidding | Wrong error message received when student enters non-numeric bid in Round 2 | High | 5
Update Bid JSON | Offset error received when (vacancy = 0 and number of round 2 pending bids = 0) | Low | 1
Mitigation: Bugs found were debugged immediately,
no extra time is needed
Final Value of Bug Metric for Iteration 5
7

## Slide 24: Challenges Faced Collecting & Using Metric
Integrating codes - New bugs were found that were previously not stated in the bug metric
New bugs found during integration were recorded & updated in the metrics, as well as solved immediately
Github commits - When files were pulled from the central repository, sometimes there were conflicts that led to loss of codes in the process. Therefore, creating bugs that were supposedly solved.
We solved this by ensuring clear communication & coordination of our commits
Errors carried forward - Some conditions of the logic didn’t fulfil all cases which caused some functions to have errors. It was challenging to find those errors, as it was thought to be accurate and correct.
We looked back on the functions we created and adjusted accordingly

## Slide 25: Use of Git

## Slide 26: Use of Git
The graph above represents the frequency of commits from iteration 1 (mid-September) to iteration 5 (mid-November)
Aside from the surge & decline in commits in the beginning & ending stages of the project respectively, the frequency of commits during the course of project was moderately consistent
The frequency of commits peaked in the period of end-September and beginning of October

## Slide 27: Use of Git
Total number of commits per member does not significantly differ from the rest of the team

## Slide 28: Main Takeaways & Issues Faced

## Slide 29: Team’s Takeaways from Project
As a project manager, we learnt how to allocate work efficiently to the different pair programmers based on their strengths and weaknesses
Debugging was always more efficient when done in a group, as anyone could provide suggestions, allowing us to learn from our peers
As a project manager, we learnt how to keep track of everyone’s work progress & make decisions accordingly
Collectively make decisions to plan a software project schedule, including buffer days

## Slide 30: Issues Faced & Resolution
Finding common time for Pair Programming
Accounting for deadlines other than SPM while assigning tasks
We discussed our other deadlines in the weekly meeting, which use to help us assign tasks accordingly
Dealing with uncertainties and unforeseen circumstances
Maximizing buffer time in our schedule
Used “recess” week to complete as many tasks as possible

## Slide 31: Finding out more about team members
Within Project:
Leadership style of each member as Project Manager
Respective strengths and weaknesses
Outside Project:
Personal interests and hobbies
Career aspirations

## Slide 32: End of SPM Final Presentation
Thank You