## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
Iteration 1
1 | 1 | Login | Admin username field was case sensitive | Low | 1 | 9 | Use the planned debugging time
2 | 1 | Student add bid, drop bid | Variable not found error when student access BIOS before admin conducts bootstrap | Low | 1
3 | 1 | Sidebar navigation | Token wasn't passed when navigating through sidebar | Low | 1
4 | 1 | Student add bid, drop bid | Submit button didn't pass token, causing student to get logged out after submitting | Low | 1
5 | 1 | Bootstrap | Temporary files were left undeleted in temp folder | Low | 1
6 | 1 | Bootstrap | The argument '0' was taken in as an empty field | Low | 1
7 | 1 | Bootstrap | There is no validation for amount when it takes in non numeric values | Low | 1
8 | 1 | Bootstrap | Maximum number of characters for userid was mistaken to be 128 instead of 100 | Low | 1
9 | 1 | Bootstrap | Validation for description was slightly wrong (e.g. if(strlen($description > 1000)) ) where strlen($description > 1000) means strlen(true). | Low | 1
Iteration 2
10 | 2 | Bootstrap | Perform bootstrapping which includes a bid from zac.ng(SOB student) for IS100 (IS course) | High | 5 | 14 | Bugs found were debugged immediately, no extra time is needed
11 | 2 | Minimum e$10 | Bids less than e$10 were successful | High | 5
12 | 2 | Error checking | When 2 errors were discovered ( Minimum bid cannot be less than e$10, you have already completed this ourse), the error numbering for both were 1 | Low | 1
13 | 2 | Error checking | When section and bid amount are left empty, no errors are shown | Low | 1
14 | 2 | Drop section | Error pops up when section is dropped!! Section has been dropped successfully but e$ has not been refunded | Low | 1
15 | 2 | Round 2 clearing | 2 students bid the same amount for one vacancy, both are suppose to fail. An error is thrown when round 2 is closed | Low | 1
Iteration 3
16 | 3 | Timetable | Bid added through bootstrapping does not show up on timetable | Low | 1 | 20 | Bugs found were debugged immediately, no extra time is needed
17 | 3 | Bootstrap | Bootstrap did not clear round2 bid table | High | 5
18 | 3 | Drop Section | Round 1.5 (after Round 1 ends, before Round 2 starts) allowed student to drop section | Low | 1
19 | 3 | Round 2 clearing | Neither successful nor unsuccesful tables are updated after Round 2 closes | High | 5
20 | 3 | Bootstrap JSON | File specific validations for a row even if common validations failed | Low | 1
21 | 3 | Bootstrap JSON | Some checks added error message to $errors instead of individual row error array | Low | 1
22 | 3 | Dump Table JSON | Keys were 'courses' and 'students' instead of 'course' and 'student' | Low | 1
23 | 3 | Update Bid JSON | Other logical validations are checked even if 'round ended' check fails | Low | 1
24 | 3 | Update Bid JSON | Section limit of 5 did not include both round 1 successful sections + round 2 bids | Low | 1
25 | 3 | Delete Bid JSON | Student did not get refunded e-$ due to calling of wrong function | Low | 1
26 | 3 | Delete Bid JSON | No such bid' check was done even if course / user / section round checks failed | Low | 1
27 | 3 | Update Bid JSON | Timetable clash check does not check for successful sections when run during Round 2 | Low | 1
Iteration 4
28 | 4 | Real time bid | Real time vacancies reflected the actual number of bids, instead of showing vacancies from round 1 (from UAT) | High | 5 | 18 | Bugs found were debugged immediately, no extra time is needed
29 | 4 | Bootstrap | Updating bid was not processed properly (from UAT) | High | 5
30 | 4 | Bootstrap JSON | Bid could not be checked and updated because the specific course section bid was used instead of only checking for course | High | 5
31 | 4 | Round 1 Clearing | Round 1 clearing did not process properly for a section with 1 vacancy | Low | 1
32 | 4 | Update Bid JSON | Did not check in the event when a student did not bid for a course for round 2 | Low | 1
33 | 4 | Update Bid JSON | Did not re-calculate minimum bid after every successful bid in round 2 | Low | 1
Iteration 5
34 | 5 | Real time bid | After a student bids during round 2, real time bid is only updated upon page refresh | Low | 1 | 7 | Bugs found were debugged immediately, no extra time is needed
35 | 5 | Round 2 bidding | Wrong error message received when student enters non-numeric bid in Round 2 | High | 5
36 | 5 | Update Bid JSON | Offset error received when (vacancy = 0 and number of round 2 pending bids = 0) | Low | 1

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login | Admin username field was case sensitive | Resolved | 2019-09-27 | 2019-10-01 | Amey / Rouhui
2 | 1 | Student add bid, drop bid | Variable not found error when student access BIOS before admin conducts bootstrap | Resolved | 2019-09-27 | 2019-09-29 | Brian / Ian
3 | 1 | Sidebar navigation | Token wasn't passed when navigating through sidebar | Resolved | 2019-09-26 | 2019-09-26 | Brian / Ian
4 | 1 | Student add bid, drop bid | Submit button didn't pass token, causing student to get logged out after submitting | Resolved | 2019-09-29 | 2019-09-29 | Brian / Ian
5 | 1 | Bootstrap | Temporary files were left undeleted in temp folder | Resolved | 2019-09-29 | 2019-09-29 | Gordon
6 | 1 | Bootstrap | The argument '0' was taken in as an empty field | Resolved | 2019-09-29 | 2019-09-29 | Gordon
7 | 1 | Bootstrap | There is no validation for amount when it takes in non numeric values | Resolved | 2019-09-29 | 2019-09-29 | Gordon
8 | 1 | Bootstrap | Maximum number of characters for userid was mistaken to be 128 instead of 100 | Resolved | 2019-09-29 | 2019-09-29 | Gordon
9 | 1 | Bootstrap | Validation for description was slightly wrong (e.g. if(strlen($description > 1000)) ) where strlen($description > 1000) means strlen(true). | Resolved | 2019-09-29 | 2019-09-29 | Gordon
10 | 2 | Bootstrap and Add bid | Perform bootstrapping which includes a bid from zac.ng(SOB student) for IS100 (IS course) | Resolved | 2019-10-08 | 2019-10-08 | Rou Hui/Brian
11 | 2 | Minimum e$10 for bidding | Bids less than e$10 were successful | Resolved | 2019-10-08 | 2019-10-08 | Rou Hui/Brian
12 | 2 | Error numbering | When 2 errors were discovered ( Minimum bid cannot be less than e$10, you have already completed this ourse), the error numbering for both were 1 | Resolved | 2019-10-08 | 2019-10-08 | Rou Hui/Brian
13 | 2 | Error checking while bidding | When section and bid amount are left empty, no errors are shown | Resolved | 2019-10-09 | 2019-10-15 | Rou Hui/Brian
14 | 2 | Drop section not refunding e$ | Error pops up when section is dropped!! Fatal error: Uncaught Error: Call to undefined function process_min_bid() in /Users/Amey/Documents/GitHub/project-g3t4/app/student_drop_section.php:78 Stack trace: #0 {main} thrown in /Users/A mey/Documents/GitHub/project-g3t4/app/student_drop_section.php on line 78 however section has been dropped successfully but e$ has not been refunded | Resolved | 2019-10-09 | 2019-10-10 | Rou Hui/Brian
15 | 2 | Round 2 clearing | 2 students bid the same amount for one vacancy, both are suppose to fail. An error is thrown when round 2 is closed | Resolved | 2019-10-15 | 2019-10-15 | Rou Hui/Brian
16 | 3 | Timetable | Bid added through bootstrapping does not show up on timetable | Resolved | 2019-10-22 | 2019-10-22 | Ian/Rou Hui
17 | 3 | Bootstrap | Bootstrap did not clear round2 bid table | Resolved | 2019-10-22 | 2019-10-22 | Ian/Rou Hui
18 | 3 | Drop Section | Round 1.5 (after Round 1 ends, before Round 2 starts) allowed student to drop section | Resolved | 2019-10-22 | 2019-10-22 | Ian/Rou Hui
19 | 3 | Round 2 clearing | Neither successful nor unsuccesful tables are updated after Round 2 closes | Resolved | 2019-10-22 | 2019-10-22 | Ian/Rou Hui
20 | 3 | Bootstrap JSON | File specific validations for a row even if common validations failed | Resolved | 2019-10-23 | 2019-10-23 | Amey/Rou Hui
21 | 3 | Bootstrap JSON | Some checks added error message to $errors instead of individual row error array | Resolved | 2019-10-23 | 2019-10-23 | Amey/Rou Hui
22 | 3 | Dump Table JSON | Keys were 'courses' and 'students' instead of 'course' and 'student' | Resolved | 2019-10-27 | 2019-10-27 | Ian/Rou Hui
23 |  | Update Bid JSON | Other logical validations are checked even if 'round ended' check fails | Resolved | 2019-10-27 | 2019-10-27 | Ian/Rou Hui
24 | 3 | Update Bid JSON | Section limit of 5 did not include both round 1 successful sections + round 2 bids | Resolved | 2019-10-27 | 2019-10-27 | Ian/Rou Hui
25 | 3 | Delete Bid JSON | Student did not get refunded e-$ due to calling of wrong function | Resolved | 2019-10-27 | 2019-10-27 | Ian/Rou Hui
26 | 3 | Delete Bid JSON | No such bid' check was done even if course / user / section round checks failed | Resolved | 2019-10-27 | 2019-10-27 | Ian/Rou Hui
27 | 3 | Update Bid JSON | Timetable clash check does not check for successful sections when run during Round 2 | Resolved | 2019-10-29 | 2019-10-29 | Brian/Gordon
28 | 4 | Real time bid | Real time vacancies reflected the actual number of bids, instead of showing vacancies from round 1 (from UAT) | Resolved | 2019-11-05 | 2019-11-05 | Brian/Gordon
29 | 4 | Bootstrap | Updating bid was not processed properly (from UAT) | Resolved | 2019-11-05 | 2019-11-05 | Brian/Gordon
30 | 4 | Bootstrap JSON | Bid could not be checked and updated because the specific course section bid was used instead of only checking for course | Resolved | 2019-11-05 | 2019-11-05 | Brian/Gordon
31 | 4 | Round 1 Clearing | Round 1 clearing did not process properly for a section with 1 vacancy | Resolved | 2019-11-05 | 2019-11-05 | Brian/Gordon
32 | 4 | Update Bid JSON | Did not check in the event when a student did not bid for a course for round 2 | Resolved | 2019-11-05 | 2019-11-05 | Brian/Gordon
33 | 4 | Update Bid JSON | Did not re-calculate minimum bid after every successful bid in round 2 | Resolved | 2019-11-05 | 2019-11-05 | Brian/Gordon
34 | 5 | Real time bid | After a student bids during round 2, real time bid is only updated upon page refresh | Resolved | 2019-11-16 | 2019-11-16 | Brian
35 | 5 | Round 2 bidding | Wrong error message received when student enters non-numeric bid in Round 2 | Resolved | 2019-11-16 | 2019-11-16 | Brian
36 | 5 | Update Bid JSON | Offset error received when (vacancy = 0 and number of round 2 pending bids = 0) | Resolved | 2019-11-17 | 2019-11-17 | Amey/Brian

## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.