## Schedule
Iteration No | Task ID | DESCRIPTION | TYPE | PLANNED DATETIME START | PLANNED DATETIME END | HOURS SPENT PLANNED | ACTUAL DATETIME START | ACTUAL DATETIME END | HOURS SPENT ACTUAL | STATUS | Is Critical Path | Not planned | Predecessor | LOCATION | FINAL COMMIT ID | PP PHOTO LINK | AR | BG | GL | IL | RH | Est Days | Act Days | Planned Prog Hrs | Prog Hrs | Non-Prog Hrs | ItrStatus | ItrNot planned
Iteration 1
1 | 1 | Iteration 1: Planning | Team Meeting - Planning, Admin, & Updates | 2019-09-19 12:00 | 2019-09-19 15:00 |  | 2019-09-19 12:00 | 2019-09-19 15:00 |  | Completed | Yes | No | NIL | [8 empty] | 0.125 | 0.125 | 0 | 0 | 0 | 1Completed | 1No
1 | 1_1 | Plan project schedule and Iteration 1 | Team Meeting - Planning, Admin, & Updates | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | Completed | Yes | No | NIL | LKS PR 2.3 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.125 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 1_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | Completed | No | No | NIL | LKS PR 2.3 | 7f061a71a453c5f30ebcf511c74e3fbba187656a |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.125 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 2 | Design database structure | Design - Other | 2019-09-20 12:00 | 2019-09-20 14:00 | 2 | 2019-09-19 15:30 | 2019-09-19 19:00 | 3.5 | Completed | Yes | No | 1_1_1 | SIS Subway |  |  |  | Attendee |  | Attendee |  | 0.083333 | 0.14583 | 0 | 0 | 3.5 | 1Completed | 1No
1 | 3 | Code student login process | Programming - Features | 2019-09-20 09:00 | 2019-09-20 12:00 |  | 2019-09-20 09:00 | 2019-09-20 15:00 |  | Completed | Yes | No | 1_2 | [8 empty] | 0.125 | 0.25 |  |  | 0 | 1Completed | 1No
1 | 3_1 | Code StudentDAO | Programming - Features | 2019-09-20 09:00 | 2019-09-20 10:00 | 1 | 2019-09-20 09:00 | 2019-09-20 11:00 | 2 | Completed | No | No | 1_2 | SIS L3 Benches | 04ee823dd7f4267738e512dd8f88072c5cd2f899 |  | Attendee |  |  |  | Attendee | 0.041667 | 0.083333 | 1 | 2 | 0 | 1Completed | 1No
1 | 3_2 | Code login interface | Programming - Features | 2019-09-21 10:00 | 2019-09-21 10:30 | 0.5 | 2019-09-20 11:00 | 2019-09-20 11:30 | 0.5 | Completed | No | No | 1_2 | SIS L3 Benches | 6d144fa99ad9f8e87077842d06d311ea0b4f0250 |  | Attendee |  |  |  | Attendee | 0.020833 | 0.020833 | 0.5 | 0.5 | 0 | 1Completed | 1No
1 | 3_3 | Code connection manager | Programming - Features | 2019-09-20 10:30 | 2019-09-20 11:00 | 0.5 | 2019-09-23 11:30 | 2019-09-23 12:00 | 0.5 | Completed | Yes | No | 1_2 | SIS L3 Benches | b6aec58bd6a5fc45343f4e26b865a9783ee873b3 |  | Attendee |  |  |  | Attendee | 0.020833 | 0.020833 | 0.5 | 0.5 | 0 | 1Completed | 1No
1 | 3_4 | Code login authentication | Programming - Features | 2019-09-21 11:00 | 2019-09-21 12:00 | 1 | 2019-09-20 12:00 | 2019-09-20 15:00 | 3 | Completed | No | No | 1_2 | SIS L3 Benches | 6d144fa99ad9f8e87077842d06d311ea0b4f0250 |  | Attendee |  |  |  | Attendee | 0.041667 | 0.125 | 1 | 3 | 0 | 1Completed | 1No
1 | 4 | Basic CSS design | Design - Other | 2019-09-20 15:00 | 2019-09-20 17:00 | 2 | 2019-09-20 12:00 | 2019-09-20 13:30 | 1.5 | Completed | No | No | 1_1_1 | Project Way | 7cd160145a2bdb90565dcfb242172dc8584e8ca5 |  |  | Attendee |  | Attendee |  | 0.083333 | 0.0625 | 0 | 0 | 1.5 | 1Completed | 1No
1 | 5 | Code remaining DAOs | Programming - Features | 2019-09-21 11:00 | 2019-09-22 15:00 | 4 | 2019-09-23 16:00 | 2019-09-25 13:00 | 7 | Completed | Yes | No | 1_2, 1_3_3 | Project Way | affb095381259000a57710e12e94944fafaac2a0 |  |  | Attendee |  | Attendee |  | 1.1667 | 1.875 | 4 | 7 | 0 | 1Completed | 1No
1 | 6 | Code common files | Programming - Features | 2019-09-23 09:00 | 2019-09-23 11:00 | 2 | 2019-09-23 17:00 | 2019-09-24 19:00 | 4 | Completed | No | No | 1_1_1 | SIS L4 | 9ca90a3375d13a6ec879348def9b9d6c3accf7b4 |  | Attendee |  |  |  | Attendee | 0.083333 | 1.0833 | 2 | 4 | 0 | 1Completed | 1No
1 | 7 | Code bootstrap | Programming - Features | 2019-09-23 16:00 | 2019-09-24 09:00 | 6 | 2019-09-24 16:00 | 2019-09-26 17:00 | 7 | Completed | Yes | No | 1_5 | Project Way | e4e0b8b1590e8efab4eec6d1fd4435be30bd6ea2 |  |  | Attendee |  | Attendee |  | 0.70833 | 2.0417 | 6 | 7 | 0 | 1Completed | 1No
1 | 8 | Integrate Code | Programming - Integration | 2019-09-26 09:00 | 2019-09-26 12:00 | 3 | 2019-09-27 12:00 | 2019-09-27 18:00 | 5 | Completed | Yes | No | 1_3_1, 1_3_2, 1_3_3, 1_3_4, 1_4, 1_6, 1_7 | SIS L4 | 28557ec07330626fc63d2546518810eb73f85372 |  | Attendee |  |  |  | Attendee | 0.125 | 0.25 | 3 | 5 | 0 | 1Completed | 1No
1 | 9 | Test Code | Testing - Integration (local) | 2019-09-26 13:00 | 2019-09-27 09:30 |  | 2019-09-27 15:00 | 2019-09-28 18:00 |  | Completed | Yes | No | 1_8 | [8 empty] | 0.85417 | 1.125 | 0 | 0 | 0 | 1Completed | 1No
1 | 9_1 | Create test cases | Testing - Updating Test Log / Test Cases | 2019-09-26 13:00 | 2019-09-26 14:30 | 1.5 | 2019-10-02 15:00 | 2019-10-02 17:00 | 2 | Completed | Yes | No | 1_8 | SIS L4 | 762eeaef30a95b73e530d566d18233b3c7380bfd |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.0625 | 0.083333 | 0 | 0 | 2 | 1Completed | 1No
1 | 9_2 | Code JSON Test Cases | Programming - Debugging | Not Planned | Not Planned | 0 | 2019-09-29 10:00 | 2019-10-01 15:00 | 2 | Completed | Yes | Yes | 1_8 | Project Way | 86895efa95cb6a9ba4bc4b2de4bcb943296e865b |  |  | Attendee | Attendee |  |  | #VALUE! | 2.2083 | 0 | 2 | 0 | 1Completed | 1Yes
1 | 9_2_1 | JSON Authentication: Login | Programming - Debugging | Not Planned | Not Planned | 0 | 2019-09-29 10:00 | 2019-09-29 13:00 | 3 | Completed | Yes | Yes | 1_8 | SIS L4 | 86895efa95cb6a9ba4bc4b2de4bcb943296e865b |  | Attendee |  | Attendee |  |  | #VALUE! | 0.125 | 0 | 3 | 0 | 1Completed | 1Yes
1 | 9_2_2 | JSON Authentication: Bootstrap | Programming - Debugging | Not Planned | Not Planned | 0 | 2019-09-29 16:00 | 2019-10-01 15:00 | 13 | Completed | Yes | Yes | 1_8 | SIS L4 | 86895efa95cb6a9ba4bc4b2de4bcb943296e865b |  | Attendee |  | Attendee |  |  | #VALUE! | 1.9583 | 0 | 13 | 0 | 1Completed | 1Yes
1 | 9_3 | Update bug log and bug metrics | Testing - Integration (local) | 2019-09-27 08:00 | 2019-09-27 09:30 | 1.5 | 2019-10-01 12:00 | 2019-10-01 15:00 | 3 | Completed | Yes | No | 1_8 | Project Way | 97db8e095e094bb33bfa6f8860ae0f164371d600 |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.0625 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 10 | Debug code | Programming - Debugging | 2019-09-27 12:00 | 2019-09-27 14:00 | 2 | 2019-09-29 13:00 | 2019-10-01 14:00 | 4 | Completed | Yes | No | 1_9_1, 1_9_2 | Project Way | e92a1dd488baca41e1b2bdfce5cc7de8f6a3260e |  |  | Attendee |  | Attendee |  | 0.083333 | 2.0417 | 2 | 4 | 0 | 1Completed | 1No
1 | 11 | Deploy to AWS | Deployment | 2019-09-27 17:00 | 2019-09-27 18:00 | 1 | 2019-10-01 16:00 | 2019-10-01 18:00 | 2 | Completed | Yes | No | 1_10 | Project Way |  |  |  | Attendee |  | Attendee |  | 0.041667 | 0.083333 | 0 | 0 | 2 | 1Completed | 1No
1 | 12 | Iteration 1: Review | Team Meeting - Planning, Admin, & Updates | 2019-09-28 08:30 | 2019-09-28 10:30 |  | 2019-09-28 10:30 | 2019-09-28 13:30 | 3 | Completed | No | No | 1_11 | SOE / SOSS GSR 3-12 | [7 empty] | 0.083333 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 12_1 | Plan Round 1 | Team Meeting - Planning, Admin, & Updates | 2019-09-28 08:30 | 2019-09-28 10:30 | 2 | 2019-09-28 10:30 | 2019-09-28 13:30 | 3 | Completed | No | No | 1_11 | SOE / SOSS GSR 3-12 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.083333 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 12_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-09-28 08:30 | 2019-09-28 10:30 | 2 | 2019-09-28 10:30 | 2019-09-28 13:30 | 3 | Completed | No | No | 1_11 | SOE / SOSS GSR 3-12 | 07b8379ca40832dc3d80123cf854a626598a9088 |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.083333 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 13 | Student Bidding | Programming - Features | 2019-09-28 11:00 | 2019-09-28 15:00 |  | 2019-09-29 15:00 | 2019-09-29 19:00 |  | Completed | No | No | 1_12_1 | [8 empty] | 0.16667 | 0.16667 |  |  | 0 | 1Completed | 1No
1 | 13_1 | Round 1: Add bid | Programming - Features | 2019-09-28 11:00 | 2019-09-28 13:00 | 2 | 2019-09-30 07:30 | 2019-09-30 09:00 | 1.5 | Completed | No | No | 1_12_1 | SIS L3 Benches | d23012857716870472ebbca7cb696c2f63c1b193 |  | Attendee |  |  |  | Attendee | 0.083333 | 0.0625 | 2 | 1.5 | 0 | 1Completed | 1No
1 | 13_2 | Round 1: View bid | Programming - Features | 2019-09-28 11:00 | 2019-09-28 13:00 | 2 | 2019-09-29 16:30 | 2019-09-29 18:30 | 2 | Completed | No | No | 1_12_1 | SIS L4 | dd438f0eae2933e7491fbe719b02ede0ccb50b63 |  |  | Attendee |  | Attendee |  | 0.083333 | 0.083333 | 2 | 2 | 0 | 1Completed | 1No
1 | 13_3 | Round 1: Drop bid | Programming - Features | 2019-09-28 13:00 | 2019-09-28 15:00 | 2 | 2019-09-30 09:00 | 2019-09-30 10:00 | 1 | Completed | No | No | 1_12_1 | SIS L3 Benches | d23012857716870472ebbca7cb696c2f63c1b193 |  | Attendee |  |  |  | Attendee | 0.083333 | 0.041667 | 2 | 1 | 0 | 1Completed | 1No
1 | 14 | Round 1: Admin Clearing Logic | Programming - Features | 2019-09-29 14:00 | 2019-09-30 12:00 | 4 | 2019-09-30 10:00 | 2019-10-01 13:30 | 3 | Completed | No | No | 1_12_1 | SIS L2 Benches | 6bcc7a166c23ee69b6ca73b8cd0dcf012e85d56d |  |  | Attendee |  | Attendee |  | 0.91667 | 1.1458 | 4 | 3 | 0 | 1Completed | 1No
1 | 15 | Iteration 1: Milestone Preparation | Milestone - Preparation | 2019-09-30 12:00 | 2019-10-02 11:00 |  | 2019-10-01 12:00 | 2019-10-01 20:00 |  | Completed | Yes | No | 1_11 | Project Way |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 1.9583 | 0.33333 | 0 | 0 | 0 | 1Completed | 1No
1 | 15_1 | PM Review Preparation | Milestone - Preparation | 2019-09-30 12:00 | 2019-10-02 11:00 | 8 | 2019-10-01 12:00 | 2019-10-01 20:00 | 8 | Completed | Yes | No | 1_11 | Project Way |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 1.9583 | 0.33333 | 0 | 0 | 8 | 1Completed | 1No
1 | 16 | PM Review | Milestone - Presentations | 2019-10-02 15:15 | 2019-10-02 16:15 | 1 | 2019-10-02 15:15 | 2019-10-02 16:15 | 1 | Completed | Yes | No | 1_15_1 | SIS SR 3-1 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 1 | 1Completed | 1No
1 | 17 | Daily Update 1 | Project Management - Update Schedule | 2019-09-21 11:00 | 2019-09-21 12:00 | 1 | 2019-09-21 11:00 | 2019-09-21 12:00 | 0.25 | Completed | No | No | NIL | PM's Home | ad115ffdf100c4d8c4d96032fdebc86e1c7918c0 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 18 | Daily Update 2 | Project Management - Update Schedule | 2019-09-22 11:00 | 2019-09-22 12:00 | 1 | 2019-09-22 11:00 | 2019-09-22 12:00 | 0.25 | Completed | No | No | 1_17 | PM's Home | 12699e890f5639e1f32e720893ff1630c1976b4d |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 19 | Daily Update 3 | Project Management - Update Schedule | 2019-09-23 11:00 | 2019-09-23 12:00 | 1 | 2019-09-23 11:00 | 2019-09-23 12:00 | 0.25 | Completed | No | No | 1_18 | SIS L3 | d5da75da64ef5c62716e1b5e102f26f8b4182fca |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 20 | Daily Update 4 | Project Management - Update Schedule | 2019-09-24 11:00 | 2019-09-24 12:00 | 1 | 2019-09-24 11:00 | 2019-09-24 12:00 | 0.25 | Completed | No | No | 1_19 | PM's Home | c0f96eb88ad36a957a1b16ba59d700e65ea50ff7 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 21 | Daily Update 5 | Project Management - Update Schedule | 2019-09-25 11:00 | 2019-09-25 12:00 | 1 | 2019-09-25 11:00 | 2019-09-25 12:00 | 0.25 | Completed | No | No | 1_20 | PM's Home | bb51027ecd46cd44716e26abc550dc4826f3361d |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 22 | Daily Update 6 | Project Management - Update Schedule | 2019-09-26 11:00 | 2019-09-26 12:00 | 1 | 2019-09-26 11:00 | 2019-09-26 12:00 | 0.25 | Completed | No | No | 1_21 | LKS Library | 5f680fc98e365a930440fda304e1678053bbddd7 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 23 | Daily Update 7 | Project Management - Update Schedule | 2019-09-27 11:00 | 2019-09-27 12:00 | 1 | 2019-09-27 11:00 | 2019-09-27 12:00 | 0.25 | Completed | No | No | 1_22 | PM's Home | 8775506564206858f826688da73a9c22fa985f55 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 24 | Daily Update 8 | Project Management - Update Schedule | 2019-09-28 11:00 | 2019-09-28 12:00 | 1 | 2019-09-28 11:00 | 2019-09-28 12:00 | 0.25 | Completed | No | No | 1_23 | PM's Home | f855c859eb64c2ef59be724bd271c8e3e95d17d9 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 25 | Daily Update 9 | Project Management - Update Schedule | 2019-09-29 11:00 | 2019-09-29 12:00 | 1 | 2019-09-29 11:00 | 2019-09-29 12:00 | 0.25 | Completed | No | No | 1_24 | PM's Home | 8652b85a78da4f1cd1d84a7b1735f2a73c7ded85 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 26 | Daily Update 10 | Project Management - Update Schedule | 2019-09-30 11:00 | 2019-09-30 12:00 | 1 | 2019-09-30 11:00 | 2019-09-30 12:00 | 0.25 | Completed | No | No | 1_25 | PM's Home | 58826ed474080f1ea950375b566b20352cf397b3 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 27 | Daily Update 11 | Project Management - Update Schedule | 2019-10-01 11:00 | 2019-10-01 12:00 | 1 | 2019-10-01 11:00 | 2019-10-01 12:00 | 0.25 | Completed | No | No | 1_26 | PM's Home | 0a571610c66227bae15418f7b24d1e15a114715e |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
1 | 28 | Daily Update 12 | Project Management - Update Schedule | 2019-10-02 11:00 | 2019-10-02 12:00 | 1 | 2019-10-02 11:00 | 2019-10-02 12:00 | 0.25 | Completed | No | No | 1_27 | PM's Home | 874a257806cbefe6c0a2db15da176d91ff1353c4 |  | Attendee | Attendee | Leader | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 1Completed | 1No
Iteration 2
2 | 1 | Iteration 2: Planning | Team Meeting - Planning, Admin, & Updates | 2019-10-03 12:00 | 2019-10-03 15:00 |  | 2019-10-02 17:00 | 2019-10-02 18:30 |  | Completed | Yes | No | NIL | [8 empty] | 0.125 | 0.0625 | 0 | 0 | 0 | 2Completed | 2No
2 | 1_1 | Plan tasks allocation and schedule | Team Meeting - Planning, Admin, & Updates | 2019-10-03 17:30 | 2019-10-03 19:00 | 3 | 2019-10-02 17:00 | 2019-10-02 18:30 | 1.5 | Completed | Yes | No | NIL | SIS Level 4 |  |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.0625 | 0.0625 | 0 | 0 | 1.5 | 2Completed | 2No
2 | 1_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-03 12:00 | 2019-10-03 13:00 | 1 | 2019-10-02 17:00 | 2019-10-02 18:30 | 0.25 | Completed | No | No | NIL | SIS Level 4 | 7e0b1037488b3dfab4d166592da65c0edcfbf722 |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.0625 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 2 | Code Round 2 | Programming - Features | 2019-10-04 09:00 | 2019-10-07 18:00 |  | 2019-10-04 09:00 | 2019-10-07 16:00 |  | Completed | Yes | No | 2_1, 2_2_3 | Project Way |  |  |  | Attendee |  |  | Attendee | 3.375 | 3.2917 |  |  | 0 | 2Completed | 2No
2 | 2_1 | View Round 1 Results | Programming - Features | 2019-10-04 09:00 | 2019-10-04 12:00 | 4 | 2019-10-04 17:00 | 2019-10-04 20:00 | 3 | Completed | No | No | 2_1 | LKS Study Booth | 9babe6b04c3ed1ced10f64bed88aaf6367824f99 |  |  | Attendee |  |  | Attendee | 0.125 | 0.125 | 4 | 3 | 0 | 2Completed | 2No
2 | 2_2 | Round 2: View Real Time Bids | Programming - Features | 2019-10-05 09:00 | 2019-10-07 18:00 | 8 | 2019-10-06 16:00 | 2019-10-07 15:00 | 11 | Completed | Yes | No | 2_1 | SOE fish tank, LKS study booth | 545f52dce61f35f6048934f1bb052dd50dbcc404 |  |  | Attendee |  |  | Attendee | 2.375 | 0.95833 | 8 | 11 | 0 | 2Completed | 2No
2 | 2_3 | Round 2: Admin Clearing Logic | Programming - Features | 2019-10-04 09:00 | 2019-10-05 15:00 | 8 | 2019-10-05 10:00 | 2019-10-07 10:00 | 8 | Completed | Yes | No | 2_1 | SIS Level 4 | 9265aee967e4f011bdd0594013ed77c8db26b0a7 |  |  | Attendee | Attendee |  |  | 1.25 | 2 | 8 | 8 | 0 | 2Completed | 2No
2 | 2_4 | View Round 2 Results | Programming - Features | 2019-10-07 13:00 | 2019-10-07 16:00 | 3 | 2019-10-08 17:00 | 2019-10-08 19:30 | 2.5 | Completed | Yes | No | 2_2_3 | SIS L3 Benches | 9265aee967e4f011bdd0594013ed77c8db26b0a7 |  |  |  | Attendee | Attendee |  | 0.125 | 0.10417 | 3 | 2.5 | 0 | 2Completed | 2No
2 | 3 | Integrate Code | Programming - Integration | 2019-10-08 11:00 | 2019-10-08 13:00 | 1 | 2019-10-08 20:00 | 2019-10-08 21:00 | 1 | Completed | Yes | No | 2_2_1, 2_2_2, 2_2_3 | SIS L3 Benches | d39df61957c05eddebb302f5ce96577379d9525c |  |  |  | Attendee | Attendee |  | 0.083333 | 0.041667 | 1 | 1 | 0 | 2Completed | 2No
2 | 4 | Test Code | Testing - Integration (local) | 2019-10-09 10:00 | 2019-10-11 14:00 |  | 2019-10-10 10:00 | 2019-10-15 15:00 |  | Completed | Yes | No | 2_3, 2_4_1, 2_4_2 |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 2.1667 | 5.2083 | 0 | 0 | 0 | 2Completed | 2No
2 | 4_1 | Create manual test cases | Testing - Updating Test Log / Test Cases | 2019-10-09 10:00 | 2019-10-12 14:00 | 6 | 2019-10-10 15:00 | 2019-10-14 19:00 | 11 | Completed | Yes | No | 2_3 | LKS Study Booth | b8bccaac24f664e4c1faf9155138d518867d263c |  | Attendee |  |  |  | Attendee | 3.1667 | 4.1667 | 0 | 0 | 11 | 2Completed | 2No
2 | 4_2 | Code JSON Test Cases | Programming - Debugging | 2019-10-09 13:00 | 2019-10-11 10:00 | 3 | 2019-10-10 11:00 | 2019-10-15 15:00 | 2 | Completed | Yes | No | 2_4_1 | SIS Level 4 |  |  | Attendee |  | Attendee |  |  | 1.875 | 5.1667 | 3 | 2 | 0 | 2Completed | 2No
2 | 4_2_1 | JSON Dumps | Programming - Debugging | 2019-10-09 13:00 | 2019-10-10 12:00 | 3 | 2019-10-10 11:00 | 2019-10-13 15:00 | 5 | Completed | No | No | 2_4_1 | SIS Level 4 | e7415d98b02300accfdbea1a7185c60944e4a3bb |  |  |  | Attendee | Attendee |  | 0.95833 | 3.1667 | 3 | 5 | 0 | 2Completed | 2No
2 | 4_2_2 | JSON Start/Stop Round | Programming - Debugging | 2019-10-09 13:00 | 2019-10-10 12:00 | 3 | 2019-10-12 10:00 | 2019-10-15 15:00 | 5 | Completed | No | No | 2_4_1 | SIS Level 4 | 15bb3452ab7f6c8bb2ac28c90568efc9a99c3856 |  |  |  | Attendee | Attendee |  | 0.95833 | 3.2083 | 3 | 5 | 0 | 2Completed | 2No
2 | 4_2_3 | JSON Student Bidding | Programming - Debugging | 2019-10-10 16:00 | 2019-10-11 10:00 | 3 | 2019-10-13 13:00 | 2019-10-15 15:00 | 12 | Completed | Yes | No | 2_4_1 | SIS Level 4 | 2934abb77db58d293c2ab3604aaeadd1bc766edb |  |  |  | Attendee | Attendee |  | 0.75 | 2.0833 | 3 | 12 | 0 | 2Completed | 2No
2 | 4_3 | Update bug metrics | Testing - Integration (local) | 2019-10-11 12:00 | 2019-10-11 14:00 | 2 | 2019-10-15 14:00 | 2019-10-15 15:00 | 1 | Completed | Yes | No | 2_4_2 | LKS Study Booth | c48145de7f1d5e57702d2fdb94ad1dce3dee965e |  | Attendee |  |  |  | Attendee | 0.083333 | 0.041667 | 0 | 0 | 1 | 2Completed | 2No
2 | 5 | Debug code | Programming - Debugging | 2019-10-12 10:00 | 2019-10-12 13:00 | 3 | 2019-10-13 12:00 | 2019-10-15 15:00 | 2 | Completed | Yes | No | 2_4_3 | Project Way | 500afc9791a0389efd181b62af28d8900cd780f7 |  |  | Attendee | Attendee |  |  | 0.125 | 2.125 | 3 | 2 | 0 | 2Completed | 2No
2 | 6 | Deploy code to AWS, test and debug | Deployment | 2019-10-13 16:00 | 2019-10-13 18:00 | 2 | 2019-10-15 13:00 | 2019-10-15 15:00 | 2 | Completed | Yes | No | 2_5 | LKS Study Booth | 5e8cd3aea75e1ffabaefebb5998ee5446962f955 |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.083333 | 0.083333 | 0 | 0 | 2 | 2Completed | 2No
2 | 7 | Iteration 2: Milestone Preparation | Milestone - Preparation | 2019-10-15 12:00 | 2019-10-14 15:00 |  | 2019-10-15 12:00 | 2019-10-15 16:00 |  | Completed | Yes | No | 2_6 | [8 empty] | -0.875 | 0.16667 | 0 | 0 | 0 | 2Completed | 2No
2 | 7_1 | Online Review Preparation | Milestone - Preparation | 2019-10-15 12:00 | 2019-10-15 15:00 | 3 | 2019-10-15 12:00 | 2019-10-15 16:00 | 4 | Completed | Yes | No | 2_6 | LKSLIB Study Booth 4-1 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.125 | 0.16667 | 0 | 0 | 4 | 2Completed | 2No
2 | 7_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-15 17:00 | 2019-10-15 18:00 | 1 | 2019-10-15 16:00 | 2019-10-15 16:10 | 0.25 | Completed | No | No | 2_6 | LKSLIB Study Booth 4-1 | 8b93322d7246442761acdb1e4b477c8f040d9e67 |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.0069444 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 8 | Online Review | Milestone - Presentations | 2019-10-16 15:15 | 2019-10-16 18:45 | 3.5 | 2019-10-16 15:15 | 2019-10-16 17:15 | 2 | Completed | Yes | No | 2_7_1 | SIS SR 3-1 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.14583 | 0.083333 | 0 | 0 | 2 | 2Completed | 2No
2 | 9 | Daily Update 1 | Project Management - Update Schedule | 2019-10-03 11:00 | 2019-10-03 12:00 | 1 | 2019-10-03 11:00 | 2019-10-03 12:00 | 0.25 | Completed | No | No | NIL | PM's Home | 250a5889a5aaade0811288e10ae2de4076b2b30d |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 10 | Daily Update 2 | Project Management - Update Schedule | 2019-10-04 11:00 | 2019-10-04 12:00 | 1 | 2019-10-04 11:00 | 2019-10-04 12:00 | 0.25 | Completed | No | No | 2_9 | PM's Home | 94fd23a38edbf3a2ae90c94f369f668094cc3237 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 11 | Daily Update 3 | Project Management - Update Schedule | 2019-10-05 11:00 | 2019-10-05 12:00 | 1 | 2019-10-05 11:00 | 2019-10-05 12:00 | 0.25 | Completed | No | No | 2_10 | PM's Home | 9229434bd9f7da938c50351d629745f21667b74f |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 12 | Daily Update 4 | Project Management - Update Schedule | 2019-10-06 11:00 | 2019-10-06 12:00 | 1 | 2019-10-06 11:00 | 2019-10-06 12:00 | 0.25 | Completed | No | No | 2_11 | PM's Home | 56adc40259cf61b352b6a121fd3d23504ff73f1d |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 13 | Daily Update 5 | Project Management - Update Schedule | 2019-10-07 11:00 | 2019-10-07 12:00 | 1 | 2019-10-07 11:00 | 2019-10-07 12:00 | 0.25 | Completed | No | No | 2_12 | PM's Home | db8e7793d8a718108e2f9310a757af8f33360105 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 14 | Daily Update 6 | Project Management - Update Schedule | 2019-10-08 11:00 | 2019-10-08 12:00 | 1 | 2019-10-08 11:00 | 2019-10-08 12:00 | 0.25 | Completed | No | No | 2_13 | PM's Home | 1da5c212dbca7fa349ac420b12d26aeb592477f3 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 15 | Daily Update 7 | Project Management - Update Schedule | 2019-10-09 11:00 | 2019-10-09 12:00 | 1 | 2019-10-09 11:00 | 2019-10-09 12:00 | 0.25 | Completed | No | No | 2_14 | PM's Home | f02ea9626deb7c0d4e9150b1b7fbd4d57717bf8e |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 16 | Daily Update 8 | Project Management - Update Schedule | 2019-10-10 11:00 | 2019-10-10 12:00 | 1 | 2019-10-10 11:00 | 2019-10-10 12:00 | 0.25 | Completed | No | No | 2_15 | PM's Home | 2392cd4aa1c6367785d6658d21c2a0f17d19b146 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 17 | Daily Update 9 | Project Management - Update Schedule | 2019-10-11 11:00 | 2019-10-11 12:00 | 1 | 2019-10-11 11:00 | 2019-10-11 12:00 | 0.25 | Completed | No | No | 2_16 | PM's Home | 9676f14590c3899266f430fb6a8e26dd88c79569 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 18 | Daily Update 10 | Project Management - Update Schedule | 2019-10-12 11:00 | 2019-10-12 12:00 | 1 | 2019-10-12 11:00 | 2019-10-12 12:00 | 0.25 | Completed | No | No | 2_17 | PM's Home | bc53b005cf3d8ef5c6363c5584e6e6e00298a8bf |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 19 | Daily Update 11 | Project Management - Update Schedule | 2019-10-13 11:00 | 2019-10-13 12:00 | 1 | 2019-10-13 11:00 | 2019-10-13 12:00 | 0.25 | Completed | No | No | 2_18 | PM's Home | 7dff0fe2999d4b13d68858219d98f3c31ea5fbb1 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 20 | Daily Update 12 | Project Management - Update Schedule | 2019-10-14 11:00 | 2019-10-14 12:00 | 1 | 2019-10-14 11:00 | 2019-10-14 12:00 | 0.25 | Completed | No | No | 2_19 | PM's Home | db14ec2f8c3986fbde914e7670cea279d807d10c |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 21 | Daily Update 13 | Project Management - Update Schedule | 2019-10-15 11:00 | 2019-10-15 12:00 | 1 | 2019-10-15 11:00 | 2019-10-15 12:00 | 0.25 | Completed | No | No | 2_20 | PM's Home | e15cf545861aecce3339ffc4d5ffd314d3997d78 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
2 | 22 | Daily Update 14 | Project Management - Update Schedule | 2019-10-16 11:00 | 2019-10-16 12:00 | 1 | 2019-10-16 11:00 | 2019-10-16 12:00 | 0.25 | Completed | No | No | 2_21 | PM's Home | 01026583676a09b0188c1c40fb0e7dfd82c067a2 |  | Leader | Attendee | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 2Completed | 2No
Iteration 3
3 | 1 | Iteration 3: Planning | Team Meeting - Planning, Admin, & Updates | 2019-10-17 10:00 | 2019-10-17 12:00 |  | 2019-10-16 18:45 | 2019-10-16 19:45 |  | Completed | Yes | No | NIL |  |  |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.083333 | 0.041667 | 0 | 0 | 0 | 3Completed | 3No
3 | 1_1 | Plan tasks allocation and schedule | Team Meeting - Planning, Admin, & Updates | 2019-10-17 10:00 | 2019-10-17 12:00 | 2 | 2019-10-16 18:45 | 2019-10-16 19:45 | 2 | Completed | Yes | No | NIL | SIS Level 4 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.083333 | 0.041667 | 0 | 0 | 2 | 3Completed | 3No
3 | 1_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-17 10:00 | 2019-10-17 12:00 | 2 | 2019-10-16 18:45 | 2019-10-16 19:45 | 1 | Completed | No | No | NIL | SIS Level 4 | 8b93322d7246442761acdb1e4b477c8f040d9e67 |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.083333 | 0.041667 | 0 | 0 | 1 | 3Completed | 3No
3 | 2 | Code timetable | Programming - Features | 2019-10-19 12:00 | 2019-10-19 13:00 | 10 | 2019-10-19 12:00 | 2019-10-20 15:00 | 6 | Completed | Yes | No | 3_1 | Project Way | b82e15b92b63a21ee349877596c75b2a38089bf6 |  |  |  |  | Attendee | Attendee | 0.041667 | 1.125 | 10 | 6 | 0 | 3Completed | 3No
3 | 3 | Code search bid | Programming - Features | 2019-10-17 12:00 | 2019-10-19 13:00 | 10 | 2019-10-25 12:00 | 2019-10-29 13:00 | 11 | Completed | Yes | No | 3_1 | SIS L3 Benches | 26423cf3c1e667e3520bda70265c2b6726819c5c |  | Attendee |  |  |  | Attendee | 2.0417 | 4.0417 | 10 | 11 | 0 | 3Completed | 3No
3 | 4 | Integrate Code | Programming - Integration | 2019-10-19 15:00 | 2019-10-20 15:00 | 2 | 2019-10-29 15:00 | 2019-10-29 17:00 | 1 | Completed | Yes | No | 3_2, 3_3 | SIS L3 Benches | 97627b6b5f86bc8efec457cb98f83aec6f828595 |  | Attendee |  |  |  | Attendee | 1 | 0.083333 | 2 | 1 | 0 | 3Completed | 3No
3 | 5 | Test Code | Testing - Integration (local) | 2019-10-17 13:00 | 2019-10-26 15:00 |  | 2019-10-30 13:00 | 2019-10-30 15:00 |  | Completed | Yes | No | 3_4, 3_5_1 | [8 empty] | 9.0833 | 0.083333 | 0 | 0 | 0 | 3Completed | 3No
3 | 5_1 | Create test cases and conduct JSON testing | Testing - Updating Test Log / Test Cases | 2019-10-17 13:00 | 2019-10-29 15:30 | 15 | 2019-10-17 13:00 | 2019-10-29 15:30 | 10 | Completed | Yes | No | 3_4 | Project Way | 79f4e0f47078c3dbc711afb5340973c1a45ae79c |  | Attendee | Attendee | Attendee | Attendee | Attendee | 12.1042 | 12.1042 | 0 | 0 | 10 | 3Completed | 3No
3 | 5_2 | Update bug log and bug metrics | Testing - Integration (local) | 2019-10-26 12:00 | 2019-10-26 15:00 | 3 | 2019-10-17 12:00 | 2019-10-29 15:00 | 4 | Completed | Yes | No | 3_5_1 | Project Way | 9be46d8a03b165bbf60f1ca58026f5c1c65467ed |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.125 | 12.125 | 0 | 0 | 4 | 3Completed | 3No
3 | 6 | Debug code | Programming - Debugging | 2019-10-27 10:00 | 2019-10-28 12:00 | 4 | 2019-10-20 12:00 | 2019-10-29 13:00 | 4 | Completed | Yes | No | 3_5_2 | SIS Level 4 | 97627b6b5f86bc8efec457cb98f83aec6f828595 |  |  | Attendee | Attendee |  |  | 1.0833 | 9.0417 | 4 | 4 | 0 | 3Completed | 3No
3 | 7 | Deploy code to AWS and Test | Testing - Deployment (cloud) | 2019-10-27 10:00 | 2019-10-27 12:00 | 1 | 2019-10-29 15:00 | 2019-10-29 15:30 | 0.5 | Completed | Yes | No | 3_6, 3_10 | SIS Level 4 |  |  |  | Attendee | Attendee |  |  | 0.083333 | 0.020833 | 0 | 0 | 0.5 | 3Completed | 3No
3 | 8 | Iteration 3: Milestone Preparation | Milestone - Preparation | 2019-10-29 12:00 | 2019-10-29 15:00 |  | 2019-10-29 12:30 | 2019-10-29 15:30 |  | Completed |  | No | 3_7 | [8 empty] | 0.125 | 0.125 | 0 | 0 | 0 | 3Completed | 3No
3 | 8_1 | UAT Preparation | Milestone - Preparation | 2019-10-29 12:00 | 2019-10-29 15:00 | 3 | 2019-10-29 12:30 | 2019-10-29 15:30 | 3 | Completed | Yes | No | 3_7 | LKSLIB Study Booth 4-3 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.125 | 0.125 | 0 | 0 | 3 | 3Completed | 3No
3 | 8_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-29 18:00 | 2019-10-29 19:00 | 1 | 2019-10-29 17:30 | 2019-10-29 18:30 | 1 | Completed | No | No | 3_7 | LKSLIB Study Booth 4-3 | 6e8df8ba50ffce8bd70457bf03b0b99e7f20a172 |  |  |  |  | Attendee |  | 0.041667 | 0.041667 | 0 | 0 | 1 | 3Completed | 3No
3 | 9 | UAT | Milestone - Presentations | 2019-10-30 15:15 | 2019-10-30 18:45 | 3.5 | 2019-10-30 15:15 | 2019-10-30 17:45 | 2.5 | Completed | Yes | No | 3_8_1 | SIS SR 3-1 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.14583 | 0.10417 | 0 | 0 | 2.5 | 3Completed | 3No
3 | 10 | UI Design | Design - Other | 2019-10-27 12:00 | 2019-10-29 18:00 | 6 | 2019-10-28 11:30 | 2019-10-28 12:30 | 1 | Completed | No | No | 3_1 | SIS Level 2 Benches | 98bdf72109e5b4cbe22746d923c35845785e43d4 |  | Attendee | Attendee |  |  |  | 2.25 | 0.041667 | 0 | 0 | 1 | 3Completed | 3No
3 | 11 | Daily Update 1 | Project Management - Update Schedule | 2019-10-17 11:00 | 2019-10-17 12:00 | 1 | 2019-10-17 11:00 | 2019-10-17 12:00 | 0.25 | Completed | No | No | NIL | PM's Home | d4209ae670427ad3128b20b61b25e99ce189ecd8 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 12 | Daily Update 2 | Project Management - Update Schedule | 2019-10-18 11:00 | 2019-10-18 12:00 | 1 | 2019-10-18 11:00 | 2019-10-18 12:00 | 0.25 | Completed | No | No | 3_11 | PM's Home | 70ac4850a80cc9d7c61efb8e4748953dd96bdba3 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 13 | Daily Update 3 | Project Management - Update Schedule | 2019-10-19 11:00 | 2019-10-19 12:00 | 1 | 2019-10-19 11:00 | 2019-10-19 12:00 | 0.25 | Completed | No | No | 3_12 | PM's Home | 981f1da6e079f3be0582bb4d0f7b3f7b9d03b328 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 14 | Daily Update 4 | Project Management - Update Schedule | 2019-10-20 11:00 | 2019-10-20 12:00 | 1 | 2019-10-20 11:00 | 2019-10-20 12:00 | 0.25 | Completed | No | No | 3_13 | PM's Home | 1b8bfadf515475744ff1d3057811366d62030b7f |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 15 | Daily Update 5 | Project Management - Update Schedule | 2019-10-21 11:00 | 2019-10-21 12:00 | 1 | 2019-10-21 11:00 | 2019-10-21 12:00 | 0.25 | Completed | No | No | 3_14 | PM's Home | 229ca2de0b0bfbdb95b7cdfd08ce51a1c5b66a1b |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 16 | Daily Update 6 | Project Management - Update Schedule | 2019-10-22 11:00 | 2019-10-22 12:00 | 1 | 2019-10-22 11:00 | 2019-10-22 12:00 | 0.25 | Completed | No | No | 3_15 | PM's Home | 53373165725da52b92827fd1e1cf8eb1f517f1ed |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 17 | Daily Update 7 | Project Management - Update Schedule | 2019-10-23 11:00 | 2019-10-23 12:00 | 1 | 2019-10-23 11:00 | 2019-10-23 12:00 | 0.25 | Completed | No | No | 3_16 | PM's Home | d9a19a6f9e15cdac7e3139ef9b46b9b574f94c17 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 18 | Daily Update 8 | Project Management - Update Schedule | 2019-10-24 11:00 | 2019-10-24 12:00 | 1 | 2019-10-24 11:00 | 2019-10-24 12:00 | 0.25 | Completed | No | No | 3_17 | PM's Home | 86c352ef7a6b076ce21f6ba98da1b2a63548e479 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 19 | Daily Update 9 | Project Management - Update Schedule | 2019-10-25 11:00 | 2019-10-25 12:00 | 1 | 2019-10-25 11:00 | 2019-10-25 12:00 | 0.25 | Completed | No | No | 3_18 | PM's Home | 9f321df15bd277e106147ad31e6cce07be8978f1 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 20 | Daily Update 10 | Project Management - Update Schedule | 2019-10-26 11:00 | 2019-10-26 12:00 | 1 | 2019-10-26 11:00 | 2019-10-26 12:00 | 0.25 | Completed | No | No | 3_19 | PM's Home | 15e17e57545cfeeeee546cf2ea261a95a7cb263b |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 21 | Daily Update 11 | Project Management - Update Schedule | 2019-10-27 11:00 | 2019-10-27 12:00 | 1 | 2019-10-27 11:00 | 2019-10-27 12:00 | 0.25 | Completed | No | No | 3_20 | PM's Home | cb4ec805806c9d51a239703fc79446b835ce81f8 |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 22 | Daily Update 12 | Project Management - Update Schedule | 2019-10-28 11:00 | 2019-10-28 12:00 | 1 | 2019-10-28 11:00 | 2019-10-28 12:00 | 0.25 | Completed | No | No | 3_21 | PM's Home | 61218f5dac665d70511c4a73190fa8f7ebf9a1ce |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 23 | Daily Update 13 | Project Management - Update Schedule | 2019-10-29 11:00 | 2019-10-29 12:00 | 1 | 2019-10-29 11:00 | 2019-10-29 12:00 | 0.25 | Completed | No | No | 3_22 | PM's Home | faffc18030bc7469943aa0c102e5f73ed486309e |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 24 | Daily Update 14 | Project Management - Update Schedule | 2019-10-30 11:00 | 2019-10-30 12:00 | 1 | 2019-10-30 11:00 | 2019-10-30 12:00 | 0.25 | Completed | No | No | 3_23 | PM's Home | 00cb1cdb77fa848b88d49686988d7fd4f84df77d |  | Attendee | Attendee | Attendee | Leader | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 3Completed | 3No
3 | 25 | Integrate changes requested in online review | Programming - Integration | Not planned | Not planned | 0 | 2019-10-18 20:00 | 2019-10-19 11:00 | 4 | Completed | No | Yes | NIL | SIS Level 4 | 9255b1bd9283a7b2bb060976db88bb0d864b5df8 |  | Attendee |  |  |  | Attendee | #VALUE! | 0.625 | 0 | 4 | 0 | 3Completed | 3Yes
Iteration 4
4 | 1 | UAT debugging | Programming - Debugging | 2019-10-31 09:00 | 2019-11-06 18:00 | 5 | 2019-10-31 09:00 | 2019-11-06 18:00 | 5 | Completed | Yes | No | NIL | Project Way | 30bbe1c2939d8091613010fbcfae3b8a14e62c93 |  | Attendee | Attendee
4 | 2 | Final Submission Preparation | Milestone - Preparation | 2019-10-31 11:00 | 2019-11-11 13:00 |  | 2019-10-31 11:00 | 2019-11-11 11:00 |  | Completed | No | No | NIL | [8 empty] | 11.0833 | 11 | 0 | 0 | 0 | 4Completed | 4No
4 | 2_1 | Preparation - Schedule | Milestone - Preparation | 2019-10-31 11:00 | 2019-11-02 11:00 | 6 | 2019-10-31 12:00 | 2019-10-31 14:00 | 5 | Completed | Yes | No | NIL | SIS Level 4 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 2 | 0.083333 | 0 | 0 | 5 | 4Completed | 4No
4 | 2_2 | Preparation - Bug Metric | Milestone - Preparation | 2019-11-03 11:00 | 2019-11-05 11:00 | 6 | 2019-11-05 10:00 | 2019-11-05 11:00 | 2 | Completed | Yes | No | 4_2_1 | SIS Level 4 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 2 | 0.041667 | 0 | 0 | 2 | 4Completed | 4No
4 | 2_3 | Preparation - Use of GIT | Milestone - Preparation | 2019-11-06 11:00 | 2019-11-08 11:00 | 6 | 2019-11-07 11:00 | 2019-11-07 12:00 | 5 | Completed | Yes | No | 4_2_2 | SIS Level 4 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 2 | 0.041667 | 0 | 0 | 5 | 4Completed | 4No
4 | 2_4 | Preparation - Others | Milestone - Preparation | 2019-11-09 11:00 | 2019-11-11 11:00 | 6 | 2019-11-05 11:00 | 2019-11-11 11:00 | 7 | Completed | Yes | No | 4_2_3 | SIS Level 4 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 2 | 6 | 0 | 0 | 7 | 4Completed | 4No
4 | 3 | Daily Update 1 | Project Management - Update Schedule | 2019-10-31 11:00 | 2019-10-31 12:00 | 1 | 2019-10-31 11:00 | 2019-10-31 12:00 | 0.25 | Completed | No | No | NIL | PM's Home | cb941f676f9daf994d68fde380a8f72d41a863ec |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 4 | Daily Update 2 | Project Management - Update Schedule | 2019-11-01 11:00 | 2019-11-01 12:00 | 1 | 2019-11-01 11:00 | 2019-11-01 12:00 | 0.25 | Completed | No | No | 4_3 | PM's Home | 389714fe90af2dbc1cc1f22b6dfaa21e6be53190 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 5 | Daily Update 3 | Project Management - Update Schedule | 2019-11-02 11:00 | 2019-11-02 12:00 | 1 | 2019-11-02 11:00 | 2019-11-02 12:00 | 0.25 | Completed | No | No | 4_4 | PM's Home | 8c4ae243ab4158eb0b74f35f255c4377e5db9be8 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 6 | Daily Update 4 | Project Management - Update Schedule | 2019-11-03 11:00 | 2019-11-03 12:00 | 1 | 2019-11-03 11:00 | 2019-11-03 12:00 | 0.25 | Completed | No | No | 4_5 | PM's Home | fa338887bb7c1e1acf2360d98338aafeeb25adcd |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 7 | Daily Update 5 | Project Management - Update Schedule | 2019-11-04 11:00 | 2019-11-04 12:00 | 1 | 2019-11-04 11:00 | 2019-11-04 12:00 | 0.25 | Completed | No | No | 4_6 | PM's Home | 9e7329718da9b42effc5119028efb90e952b6b2d |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 8 | Daily Update 6 | Project Management - Update Schedule | 2019-11-05 11:00 | 2019-11-05 12:00 | 1 | 2019-11-05 08:00 | 2019-11-05 09:00 | 0.25 | Completed | No | No | 4_7 | PM's Home | 9e007895edb5a3ade07e808b3c79aa650e8e51ce |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 9 | Daily Update 7 | Project Management - Update Schedule | 2019-11-06 11:00 | 2019-11-06 12:00 | 1 | 2019-11-06 11:00 | 2019-11-06 12:00 | 0.25 | Completed | No | No | 4_8 | PM's Home | ec52df253d27aca00a926ea15c72c97a30407833 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 10 | Daily Update 8 | Project Management - Update Schedule | 2019-11-07 11:00 | 2019-11-07 12:00 | 1 | 2019-11-07 11:00 | 2019-11-07 12:00 | 0.25 | Completed | No | No | 4_9 | PM's Home | 92d2b92b3a4767a74910c9467dfaf7e616452210 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 11 | Daily Update 9 | Project Management - Update Schedule | 2019-11-08 11:00 | 2019-11-08 12:00 | 1 | 2019-11-08 11:00 | 2019-11-08 12:00 | 0.25 | Completed | No | No | 4_10 | PM's Home | a622e67d968537a5babe26f19e607facc53dafa5 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 12 | Daily Update 10 | Project Management - Update Schedule | 2019-11-09 11:00 | 2019-11-09 12:00 | 1 | 2019-11-09 11:00 | 2019-11-09 12:00 | 0.25 | Completed | No | No | 4_11 | PM's Home | 97c11ceebdd2efcbed9945fd351b269d2d8f16c9 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 13 | Daily Update 11 | Project Management - Update Schedule | 2019-11-10 11:00 | 2019-11-10 12:00 | 1 | 2019-11-10 11:00 | 2019-11-10 12:00 | 0.25 | Completed | No | No | 4_12 | PM's Home | 3fc6312a058022b279942790e45673c9d51f7850 |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 14 | Daily Update 12 | Project Management - Update Schedule | 2019-11-11 11:00 | 2019-11-11 12:00 | 1 | 2019-11-11 10:00 | 2019-11-10 11:00 | 0.25 | Completed | No | No | 4_13 | PM's Home | 758d43bb81eef94752ffca09d957e728d4efde6d |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | -0.95833 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 15 | Daily Update 13 | Project Management - Update Schedule | 2019-11-12 11:00 | 2019-11-12 12:00 | 1 | 2019-11-12 11:00 | 2019-11-12 12:00 | 0.25 | Completed | No | No | 4_14 | PM's Home | 4cf2c4d637dea4d2c6aedea18bab4d397a086e9d |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
4 | 16 | Daily Update 14 | Project Management - Update Schedule | 2019-11-13 11:00 | 2019-11-13 12:00 | 1 | 2019-11-13 11:00 | 2019-11-13 12:00 | 0.25 | Completed | No | No | 4_15 | PM's Home | f73c0e3a5d560d45941d48ebc46fd6e7d57eab7e |  | Attendee | Leader | Attendee | Attendee | Leader | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 4Completed | 4No
Iteration 5
5 | 1 | Final submission review | Milestone - Preparation | 2019-11-13 11:00 | 2019-11-16 11:00 | 5 | 2019-11-13 11:00 | 2019-11-16 11:00 | 4 | Completed | Yes | No | NIL | SIS Level 4 |  |  | Attendee | Leader | Attendee | Attendee | Attendee
5 | 2 | Final Submission | Other | 2019-11-17 11:00 | 2019-11-17 23:59 | 1 | 2019-11-17 12:00 | 2019-11-17 17:00 | 1 | Completed | Yes | No | 5_1 | SIS Level 4 |  |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.54097 | 0.20833 | 0 | 0 | 1 | 5Completed | 5No
5 | 3 | Final Presentation Preparation and Minutes | Milestone - Preparation | 2019-11-14 12:00 | 2019-11-17 12:00 | 2 | 2019-11-16 13:00 | 2019-11-16 15:30 | 3.5 | Completed | Yes | No | 5_2 | SIS Level 4 | 1dd685840e377cf4a7a857da535ff840a3d6caeb |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.0625 | 0.10417 | 0 | 0 | 3.5 | 5Completed | 5No
5 | 4 | Final Presentation | Milestone - Presentations | 2019-11-18 15:30 | 2019-11-18 17:00 | 1.5 | 2019-11-18 15:30 | 2019-11-18 17:00 | 0.17 | Not started | Yes | No | 5_3 | SIS SR2.1 |  |  | Attendee | Leader | Attendee | Attendee | Attendee
5 | 5 | Daily Update 1 | Project Management - Update Schedule | 2019-11-14 11:00 | 2019-11-14 12:00 | 1 | 2019-11-14 11:00 | 2019-11-14 12:00 | 0.25 | Completed | No | No | NIL | PM's Home | e6704d96e55dfce9503cd8f14354eaf0530568a9 |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 5Completed | 5No
5 | 6 | Daily Update 2 | Project Management - Update Schedule | 2019-11-15 11:00 | 2019-11-15 12:00 | 1 | 2019-11-15 11:00 | 2019-11-15 12:00 | 0.25 | Completed | No | No | 5_5 | PM's Home | 606140d9bcde5c190c8424e5f934a84d14df9032 |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 5Completed | 5No
5 | 7 | Daily Update 3 | Project Management - Update Schedule | 2019-11-16 11:00 | 2019-11-16 12:00 | 1 | 2019-11-16 11:00 | 2019-11-16 12:00 | 0.25 | Completed | No | No | 5_6 | PM's Home | 885c237ae07632161ad7c645d5924399ae92015e |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 5Completed | 5No
5 | 8 | Daily Update 4 | Project Management - Update Schedule | 2019-11-17 11:00 | 2019-11-17 12:00 | 1 | 2019-11-17 11:00 | 2019-11-17 12:00 | 0.25 | Completed | No | No | 5_7 | LKS Library | dc3ad4279b9a60fff6db345ebcc09427f9921c83 |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.041667 | 0.041667 | 0 | 0 | 0.25 | 5Completed | 5No
5 | 9 | Daily Update 5 | Project Management - Update Schedule | 2019-11-18 11:00 | 2019-11-18 12:00 | 1 | 2019-11-17 23:00 | 2019-11-17 23:30 |  | Not started | No | No | 5_8 | SIS Level 4 |  |  | Attendee | Leader | Attendee | Attendee | Attendee | 0.041667 | 0.020833 | 0 | 0 | 0 | 5Not started | 5No
5 | 10 | Code bid status JSON | Programming - Debugging | Not planned | Not planned | 0 | 2019-11-16 16:00 | 2019-11-16 17:00 | 1 | Completed | Yes | Yes | NIL | Project Way | 1dd685840e377cf4a7a857da535ff840a3d6caeb |  | Attendee | Attendee |  |  |  | #VALUE! | 0.041667 | 0 | 1 | 0 | 5Completed | 5Yes
5 | 11 | Final testing and debugging of front-end and JSON | Programming - Debugging | Not planned | Not planned | 0 | 2019-11-17 13:00 | 2019-11-17 14:00 | 1 | Completed | No | Yes | NIL | SIS Level 4 | 00aeb1ace5b163e6333ec5987da3d3a4b15ce910 |  | Attendee | Attendee |  |  |  | #VALUE! | 0.041667 | 0 | 1 | 0 | 5Completed | 5Yes

## Metrics
Burndown
Iteration No. | Planned | Actual
1 | 69 | 97.5
2 | 74.5 | 77
3 | 76.5 | 54.5
4 | 43 | 27.5
5 | 14.5 | 11.67
Task Completion Check
§Actual tasks / Estimated tasks completed
Iteration No. | Planned Tasks | Completed Tasks | Value
1 | 42 | 45 | 1.0714
2 | 36 | 36 | 1
3 | 30 | 31 | 1.0333
4 | 20 | 19 | 0.95
5 | 9 | 8 | 0.88889
Iteration Completion Check
§Estimated time / actual time
Iteration No. | Estimated time | Actual Time | Value
1 | 10.0208 | 12.875 | 0.77832
2 | 17.75 | 32.9653 | 0.53845
3 | 29.0833 | 39.7708 | 0.73127
4 | 19.6667 | 16.75 | 1.1741
5 | 0.81181 | 0.5 | 1.6236
Load factor
Hours/Day | planned and actual per iteration
Iteration No. | Planned Hrs | Actual Hrs
1 | 69 | 79.5
2 | 74.5 | 77
3 | 76.5 | 50.5
4 | 43 | 27.5
5 | 14.5 | 9.67
Hours spent per member
| AR | BG | GL | IL | RH
Prog Hrs | 53.5 | 55 | 59.5 | 54.5 | 53.5
Non-prog Hrs | 109.5 | 105 | 97 | 104.5 | 108.5
Pair programming time check
Estimated PP hours/actual PP hours (per task)
0.5
0.57143
0.5
1.3333
1
2
1.3333
1.3333
0.72727
1
1.2

## Support
Raise any problems or questions in the eLearn Discussion Forum

## Config
Leader
Attendee
Programming - Features
Programming - Debugging
Programming - Integration
Deployment
Testing - Integration (local)
Testing - Deployment (cloud)
Testing - Updating Test Log / Test Cases
Team Meeting - Planning, Admin, & Updates
Team Meeting - Knowledge Sharing
Team Meeting - Update Minutes
Team Meeting - Other
Project Management - Update Schedule
Project Management - Update Metrics
Project Management - Other
Design - App Architecture (SD etc)
Design - Use Cases
Design - Other
Milestone - Preparation
Milestone - Presentations
Other
Yes
No
Not started
Started
Completed
Incomplete
Hold