## Week 6
Person | Question | Week: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | Code connection manager and protect files | Code token, common, JWT
| What will you do today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files | Replace session authentication with token authentication
| Do you have any obstacles? | NIL | Windows and Mac have different default SQL credentials so was stuck for awhile | Realised that we authenticated by session instead of token
Rou Hui | What did you do yesterday? | Non-working day | Code connection manager and protect files | Code token, common, JWT
| What will you work on today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files | Replace session authentication with token authentication
| Do you have any obstacles? | NIL | Windows and Mac have different default SQL credentials so was stuck for awhile | Realised that we authenticated by session instead of token
Brian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out | Code CourseCompletedDAO and PrerequisiteDAO
| What will you work on today? | Start coding DAOs | Code remaining DAOs | Finish up coding remaining DAOs (Bid, BiddingRound, Round1)
| Do you have any obstacles? | NIL | Integrating StudentDAO done by other pair with our version of StudentDAO | Had to fix some foreign key errors in SQL
Ian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out | Code CourseCompletedDAO and PrerequisiteDAO
| What will you work on today? | Start coding DAOs | Code remaining DAOs | Finish up coding remaining DAOs (Bid, BiddingRound, Round1)
| Do you have any obstacles? | NIL | Integrating StudentDAO done by other pair with our version of StudentDAO | Had to fix some foreign key errors in SQL
Gordon | What did you do yesterday? | Check forum, project wiki and update requirements and finalize schedule | Non-working day | PM Review preparation for week 7
| What will you work on today? | Non-working day | PM Review preparation for week 7 | Non-working day
| Do you have any obstacles? | NIL | NIL | Realised there were many things to think about on scheduling