## Slide 1: PM Review G3-T4 Gordon, Amey, Brian, Rou Hui, Ian

## Slide 2: AGENDA
Functionalities
Schedule
Bug Metrics
Roles & Responsibilities
Pair programming teams & Rotation plan

## Slide 3: FUNCTIONALITIES
1

## Slide 4: FUNCTIONALITIES
Team’s plans to add functionalities:
Student’s timetable
Searching for classes
Plans to use any PHP Frameworks?
No
Tight deadlines, may not have enough time to learn
Web application required isn’t too complex

## Slide 5: FUNCTIONALITIES
Functionalities Completed:
Login
Bootstrap
Round 1 Bidding
Round 1 Closing
IP Address:
18.139.162.53
Admin Password:
P@ssword1

## Slide 6: SCHEDULE
2

## Slide 7: TEAM SCHEDULE
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Iteration 2
Iteration 1
Iteration 3
Week 12
Week 13
Interim Review Presentation
2 Oct
Status Review
16 Oct
UAT
30 Oct
Final Presentation
20 Nov
Iteration 4
Week 14
19 Sept – 2 Oct
(14 Days)
3 Oct – 16 Oct
(14 Days)
17 Oct – 30 Oct
(14 Days)
7 Nov – 20 Nov
(14 Days)

## Slide 8: Iteration Tasks
Week 5
Week 6
  Project Manager: Gordon
Iteration 1: Planning – All Members
Design database structure – Brian & Ian
Code student login process– Amey & Rou Hui
Basic CSS design– Brian & Ian
Code remaining DAOs – Brian & Ian
Code common files – Amey & Rou Hui
Code bootstrap– Brian & Ian
Integrate code– Amey & Rou Hui
Iteration 1
Week 7

## Slide 9: Iteration Tasks
Week 5
Week 6
  Project Manager: Gordon
Test code – All Members
Debug code – Brian & Ian
Deploy to AWS – Brian & Ian
Iteration 1: Second meeting (Plan round 1) – All members
Student bidding (add, drop) – Amey & Rou Hui
Student bidding (view results) – Brian & Ian
Round 1: Admin Clearing Logic – Brian & Ian
Iteration 1: Third meeting (PM review prep) – All members
PM review– All members
Iteration 1
Week 7
Continued…

## Slide 10: Iteration Tasks
Week 7
Week 8
Project Manager: Amey
Iteration 2: Planning – All members
Round 2 View Real Time Bids – Gordon & Ian
Round 2 Clearing Logic and View Results – Brian & Rou Hui
Integrate code – Gordon & Ian
Test code – All members
Debug code – Brian & Rou Hui
Deploy code to AWS – Gordon & Ian
Online Review Preparation – All members
Online review – Gordon & Ian
Iteration 2
Week 9

## Slide 11: Iteration Tasks
Week 9
Week 10
Project Manager: Ian
Iteration 3: Planning – All members
Code timetable – Gordon & Rouhui
Code search bid – Amey & Brian
Integrate code – Gordon & Rouhui
Test code – All members
Debug code – Amey & Brian
Deploy to AWS – Gordon & Rouhui
Iter 3 second meeting – All members
UI Design– Amey & Brian
UAT – All members
Iteration 3
Week 11

## Slide 12: Iteration Tasks
Week 12
Project Manager: Brian
Preparation - Schedule – All members
Preparation - Bug Metric – All members
Preparation - Use of GIT – All members
Preparation - Others – All members
Final Presentation – All members
Iteration 4
Week 13
Week 14

## Slide 13: MILESTONES
Week 7
Milestone 1
PM Review
Week 9
Milestone 2
Application Demo and Progress Update
Week 11
Milestone 3
User Acceptance Test (UAT)
Week 14
Milestone 4
Final Presentation

## Slide 14
1_1_1 → 1_2 → 1_3_3 → 1_5 → 1_7 → 1_8 → 1_9_1, 1_9_2 → 1_10 → 1_11 → 1_15_1 → 1_16

## Slide 15
2_1
1
1
1
1
0
1
2_2_1
2
1
2
4
2
4
2_2_2
2
3
4
2
0
4
2_2_3
2
2
3
2
0
3
2_3
5
1
5
5
0
5
2_2_4
4
1
4
4
0
4
2_4_1
6
1
6
6
0
6
2_4_2
7
3
9
7
0
9
2_4_3
10
1
10
10
0
10
2_5
11
1
11
11
0
11
2_6
12
1
12
12
0
12
2_7_1
13
1
13
13
0
13
2_8
14
1
14
14
0
14
Plan iter 2
View round 1 results
Round 2 view bid
Round 2 admin clearing
View round 2 results
Integrate code
Create test cases
JSON authentication, update bug log
Update bug metrics
Debug code
Deploy code to AWS
Online review prep
Online review
Critical Path – Iteration 2
2_1 → 2_2_2 → 2_3 → 2_4_1 → 2_4_2 → 2_4_3 → 2_5 → 2_6 → 2_7_1 → 2_8
2_1 → 2_2_3 → 2_2_4 → 2_3 → 2_4_1 → 2_4_2 → 2_4_3 → 2_5 → 2_6 → 2_7_1 → 2_8

## Slide 16
3_1
1
1
0
1
1
1
3_2
3
4
0
2
2
4
3
4
0
2
2
4
3_3
3_4
1
5
0
5
5
5
3_5_1
1
6
0
6
6
6
3_5_2
1
7
0
7
7
7
3_6
2
0
8
9
8
9
3_7
1
10
0
10
10
10
3_8_1
3
13
0
11
11
13
3_9
1
14
0
14
14
14
3_10
3
4
5
7
2
9
Plan iter 3
Code timetable
Code bid search
Integrate code
Create test cases
Update bug log & bug metrics
Debug code
Deploy to AWS
UAT Preparation
UAT
UI Design
Critical Path – Iteration 3
3_1 → 3_2, 3_3 → 3_4 → 3_5_1 → 3_5_2 → 3_6 → 3_7 → 3_8_1 → 3_9

## Slide 17
4_1_1
3
3
0
3
1
1
4_1_2
3
6
0
6
4
4
4_1_3
3
9
0
9
7
7
4_1_4
3
12
0
12
10
10
4_2
1
13
0
13
13
13
Preparation - Schedule
Preparation - Bug metric
Preparation - Use of GIT
Preparation - Others
Final Presentation
Critical Path – Iteration 4
4_1_1 → 4_1_2 → 4_1_3 → 4_1_4 → 4_2

## Slide 18: BUG METRICS
3

## Slide 19: Bug Metrics
S/N | Iter | Function | Description | Severity | Points | Final Bug Metric (Total)
1 | 1 | Login | Admin username field was case sensitive | Low | 1 | 9
2 | 1 | Student add bid, drop bid | Variable not found error when student access BIOS before admin conducts bootstrap | Low | 1 | 
3 | 1 | Sidebar navigation | Token wasn't passed when navigating through sidebar | Low | 1 | 
4 | 1 | Student add bid, drop bid | Submit button didn't pass token, causing student to get logged out after submitting | Low | 1 | 

## Slide 20: Bug Metrics
S/N | Iter | Function | Description | Severity | Points | Final Bug Metric (Total)
5 | 1 | Bootstrap | Temporary files were left un-deleted in temp folder | Low | 1 | 9
6 | 1 | Bootstrap | The argument '0' was taken in as an empty field | Low | 1 | 
7 | 1 | Bootstrap | There is no validation for amount when it takes in non numeric values | Low | 1 | 
8 | 1 | Bootstrap | Maximum number of characters for userid was mistaken to be 128 instead of 100 | Low | 1 | 
9 | 1 | Bootstrap | Validation for description was slightly wrong (e.g. if(strlen($description > 1000)) ) where strlen($description > 1000) means strlen(true). | Low | 1 | 

## Slide 21: Bug Metrics
Mitigation: Use the planned debugging time in the iteration
Final Value of Bug Metric
9

## Slide 22: ROLES & RESPONSIBILITIES
4

## Slide 23: PROJECT MANAGER ROTATION
PM: Gordon
Coders: Brian, Ian, Amey, Rou Hui
PM: Amey
Coders: Brian, Ian, Gordon, Rou Hui
PM: Ian
Coders: Brian, Gordon, Amey, Rou Hui
PM: Brian
Coders: N.A
Iteration 1
Iteration 2
Iteration 3
Iteration 4

## Slide 24: PAIR PROGRAMMING TEAMS
5

## Slide 25: PP Teams & Rotation Plan
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Iteration 2
Iteration 1
Iteration 3
Week 12
Week 13
Interim Review Presentation
2 Oct
Status Review
16 Oct
UAT
30 Oct
Final Presentation
20 Nov
Iteration 4
Week 14
PM: Gordon
Pair 1: Brian + Ian
Pair 2: Amey + Rou Hui
PM: Amey
Pair 1: Gordon + Ian
Pair 2: Brian + Rou Hui
PM: Ian
Pair 1: Gordon & Rou Hui
Pair 2: Brian & Amey
PM: Brian

## Slide 26: End of PM Review
Thank you