## Week 5
Person | Question | Week: 30 September 2019 to 6 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non working day
| What will you do today? | Code student add bid and drop bid
| Do you have any obstacles? | Coding round 1 features (eg. add bid) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet
Rou Hui | What did you do yesterday? | Non working day
| What will you work on today? | Code student add bid and drop bid
| Do you have any obstacles? | Coding round 1 features (eg. add bid) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet
Brian | What did you do yesterday? | Debug code according to bug log, and code student view bid
| What will you work on today? | Code round 1 clearing logic
| Do you have any obstacles? | Coding round 1 features (eg. view results) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet
Ian | What did you do yesterday? | Debug code according to bug log, and code student view bid
| What will you work on today? | Code round 1 clearing logic
| Do you have any obstacles? | Coding round 1 features (eg. view results) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet
Gordon | What did you do yesterday? | Non working day
| What will you work on today? | Deployment to AWS
| Do you have any obstacles? | No Issues