## Week 6
Person | Question | Week: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | Code connection manager and protect files | Code token, common, JWT | Replace session authentication with token authentication for student
| What will you do today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files | Replace session authentication with token authentication | Replace session authentication with token authentication for admin
| Do you have any obstacles? | No issues | Windows and Mac have different default SQL credentials so was stuck for awhile | Realised that we authenticated by session instead of token | Initially, wasn't sure that we were supposed to pass token using $_GET on every page
Rou Hui | What did you do yesterday? | Non-working day | Code connection manager and protect files | Code token, common, JWT | Replace session authentication with token authentication for student
| What will you work on today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files | Replace session authentication with token authentication | Replace session authentication with token authentication for admin
| Do you have any obstacles? | No issues | Windows and Mac have different default SQL credentials so was stuck for awhile | Realised that we authenticated by session instead of token | Initially, wasn't sure that we were supposed to pass token using $_GET on every page
Brian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out | Code CourseCompletedDAO and PrerequisiteDAO | Code BiddingRoundDAO, Round1DAO, admin home
| What will you work on today? | Start coding DAOs | Code remaining DAOs | Finish up coding remaining DAOs (Bid, BiddingRound, Round1) | Code admin controls, eg. navigation for bootstrap, round management
| Do you have any obstacles? | No issues | Integrating StudentDAO done by other pair with our version of StudentDAO | Had to fix some foreign key errors in SQL | Difficulty coding Round 1 related DAOs without Round 1 clearing logic code
Ian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out | Code CourseCompletedDAO and PrerequisiteDAO | Code BiddingRoundDAO, Round1DAO, admin home
| What will you work on today? | Start coding DAOs | Code remaining DAOs | Finish up coding remaining DAOs (Bid, BiddingRound, Round1) | Code admin controls, eg. navigation for bootstrap, round management
| Do you have any obstacles? | No issues | Integrating StudentDAO done by other pair with our version of StudentDAO | Had to fix some foreign key errors in SQL | Difficulty coding Round 1 related DAOs without Round 1 clearing logic code
Gordon | What did you do yesterday? | Check forum, project wiki and update requirements and finalize schedule | Non-working day | PM Review preparation for week 7 | Non-working day
| What will you work on today? | Non-working day | PM Review preparation for week 7 | Non-working day | Code boostrap
| Do you have any obstacles? | No issues | No issues | Realised there were many things to think about on scheduling | No issues