## Week 5
Person | Question | Week: 16 September 2019 to 22 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | [5 empty] | Created login page | Finished authentication/error handling of login page
| What will you do today? | [5 empty] | Work on the authentication/error handling of login page | Non-working day
| Do you have any obstacles? | [5 empty] | There were some errors regarding error messages, and some corner cases like entering an invalid username were also tackled | User could access some pages without logging in, indicating that we need to do a protect.php page
Rou Hui | What did you do yesterday? | [5 empty] | Created login page | Finished authentication/error handling of login page
| What will you work on today? | [5 empty] | Work on the authentication/error handling of login page | Non-working day
| Do you have any obstacles? | [5 empty] | There were some errors regarding error messages, and some corner cases like entering an invalid username were also tackled | User could access some pages without logging in, indicating that we need to do a protect.php page
Brian | What did you do yesterday? | [5 empty] | Draw ER diagram and create database tables in SQL | Create student home page, basic add/view/drop bid pages, css stylesheet
| What will you work on today? | [5 empty] | Create student home page and sidebar navigation | Non-working day
| Do you have any obstacles? | [5 empty] | Had some issues loading data into SQL, realised it was because we used "\n" instead of "\r\n" for csv new line | Integrating different variable names used by team members and I for DAO classes
Ian | What did you do yesterday? | [5 empty] | Draw ER diagram and create database tables in SQL | Create student home page, basic add/view/drop bid pages, css stylesheet
| What will you work on today? | [5 empty] | Create student home page and sidebar navigation | Non-working day
| Do you have any obstacles? | [5 empty] | Had some issues loading data into SQL, realised it was because we used "\n" instead of "\r\n" for csv new line | Integrating different variable names used by team members and I for DAO classes
Gordon | What did you do yesterday? | [5 empty] | Created a directory structure | Scheduling for the project
| What will you work on today? | [5 empty] | Do up the schedule for the entire project | Check forum, project wiki and update requirements and finalize schedule
| Do you have any obstacles? | [5 empty] | None | Difficulty estimating work done for each task

## Week 6
Person | Question | Week: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | Code connection manager and protect files | Code token, common, JWT | Replace session authentication with token authentication for student | Code bootstrap and admin control pages | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1
| What will you do today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files | Replace session authentication with token authentication | Replace session authentication with token authentication for admin | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1 | Non-working day
| Do you have any obstacles? | No issues | Windows and Mac have different default SQL credentials so was stuck for awhile | Realised that we authenticated by session instead of token | Initially, wasn't sure that we were supposed to pass token using $_GET on every page | Had to wait for other pair to finish admin_round and admin_bootstrap in order to token protect their files | Creating test cases made us discover that there were missing validations in the code | No issues
Rou Hui | What did you do yesterday? | Non-working day | Code connection manager and protect files | Code token, common, JWT | Replace session authentication with token authentication for student | Replace session authentication with token authentication for admin | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1
| What will you work on today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files | Replace session authentication with token authentication | Replace session authentication with token authentication for admin | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1 | Non-working day
| Do you have any obstacles? | No issues | Windows and Mac have different default SQL credentials so was stuck for awhile | Realised that we authenticated by session instead of token | Initially, wasn't sure that we were supposed to pass token using $_GET on every page | Had to wait for other pair to finish admin_round and admin_bootstrap in order to token protect their files | Creating test cases made us discover that there were missing validations in the code | No issues
Brian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out | Code CourseCompletedDAO and PrerequisiteDAO | Code BiddingRoundDAO, Round1DAO, admin home | Code bootstrap and admin control pages | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1
| What will you work on today? | Start coding DAOs | Code remaining DAOs | Finish up coding remaining DAOs (Bid, BiddingRound, Round1) | Code admin controls, eg. navigation for bootstrap, round management | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1 | Debug code according to bug log, and code student view bid
| Do you have any obstacles? | No issues | Integrating StudentDAO done by other pair with our version of StudentDAO | Had to fix some foreign key errors in SQL | Difficulty coding Round 1 related DAOs without Round 1 clearing logic code | Bootstrap was tedious to code as bugs were hard to detect | Creating test cases made us discover that there were missing validations in the code | No issues
Ian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out | Code CourseCompletedDAO and PrerequisiteDAO | Code BiddingRoundDAO, Round1DAO, admin home | Code bootstrap and admin control pages | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1
| What will you work on today? | Start coding DAOs | Code remaining DAOs | Finish up coding remaining DAOs (Bid, BiddingRound, Round1) | Code admin controls, eg. navigation for bootstrap, round management | Integrate code, create test cases and bug log/metric for existing functions | Second meeting for iteration 1 | Debug code according to bug log, and code student view bid
| Do you have any obstacles? | No issues | Integrating StudentDAO done by other pair with our version of StudentDAO | Had to fix some foreign key errors in SQL | Difficulty coding Round 1 related DAOs without Round 1 clearing logic code | Bootstrap was tedious to code as bugs were hard to detect | Creating test cases made us discover that there were missing validations in the code | No issues
Gordon | What did you do yesterday? | Check forum, project wiki, update on requirements and schedule | Non-working day | PM Review preparation for week 7 | Non-working day | Critical path and schedule | Non-working day | Second meeting for iteration 1
| What will you work on today? | Non-working day | PM Review preparation for week 7 | Non-working day | Critical path and schedule | Non-working day | Second meeting for iteration 1 | Non-working day
| Do you have any obstacles? | No issues | No issues | Realised there were many things to think about on scheduling | No issues | Many tasks were missing in schedule for the critical path | No issues | No issues

## Week 7
Person | Question | Week: 30 September 2019 to 6 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non working day | Code student add bid and drop bid | PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review and Iteration 2 kick off meeting | Work on schedule | JSON test cases | JSON
| What will you do today? | Code student add bid and drop bid | PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review | Adjust schedule such that we can add iteration 5 | Start coding JSON test cases | NIL | NIL
| Do you have any obstacles? | Coding round 1 features (eg. add bid) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet | No issues | Amazon reads csv files differently from how our local machine reads it | Nope | NIL | The working of JSON took some time to understand | JSON test case implementation took time to understand
Rou Hui | What did you do yesterday? | Non working day | Code student add bid and drop bid | PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review and Iteration 2 Planning Meeting | Code View Round 1 results and debugged integration bugs from Iteration 1 | Finished coding Round 2 add bid logic and started coding Round 2 real-time view bid viewer | Finished coding front end UI of round 2 view real time bids
| What will you work on today? | Code student add bid and drop bid | PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review | Code View Round 1 results, and start coding Round 2 view bid | Start coding Round 2 view bid | Continue coding Round 2 real-time bid viewer | Non working day
| Do you have any obstacles? | Coding round 1 features (eg. add bid) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet | No issues | Amazon reads csv files differently from how our local machine reads it | Have to add Iteration 5 to our plan, so existing schedule has to be changed | Newly discovered integration bugs, didn't have time to start Round 2 view bid yesterday | Schedule didn't account for Round 2 add bid logic (as we thought it was the same as Round 1 add bid logic), but it took longer than expected | NIL
Brian | What did you do yesterday? | Debug code according to bug log, and code student view bid | Code round 1 clearing logic 1st half | Code round 1 clearing logic 2nd half, PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review and Iteration 2 Planning Meeting | Code View Round 1 results and debugged integration bugs from Iteration 1 | Finished coding Round 2 add bid logic and started coding Round 2 real-time view bid viewer | Finished coding front end UI of round 2 view real time bids
| What will you work on today? | Code round 1 clearing logic | Code round 1 clearing logic 2nd half, PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review | Code View Round 1 results, and start coding Round 2 view bid | Start coding Round 2 view bid | Continue coding Round 2 real-time bid viewer | Non working day
| Do you have any obstacles? | Coding round 1 features (eg. view results) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet | Too many logics to understand along the way | Amazon reads csv files differently from how our local machine reads it | Have to add Iteration 5 to our plan, so existing schedule has to be changed | Newly discovered integration bugs, didn't have time to start Round 2 view bid yesterday | Schedule didn't account for Round 2 add bid logic (as we thought it was the same as Round 1 add bid logic), but it took longer than expected | NIL
Ian | What did you do yesterday? | Debug code according to bug log, and code student view bid | Code round 1 clearing logic | Code round 1 clearing logic 2nd half, PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review and Iteration 2 Planning Meeting | Add session authentication to student and admin | Manage round 2 | None
| What will you work on today? | Code round 1 clearing logic | Code round 1 clearing logic 2nd half, PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review | Add session authentication to student and admin | Non working day | None | Round 2 live view
| Do you have any obstacles? | Coding round 1 features (eg. view results) involves planning ahead to ensure feature integrates with round 2, which is difficult as round 2 code is not done yet | Too many logics to understand along the way | Amazon reads csv files differently from how our local machine reads it | Have to add Iteration 5 to our plan, so existing schedule has to be changed | None | None | None
Gordon | What did you do yesterday? | Non working day | Non working day | PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review and Iteration 2 Planning Meeting | Add session authentication to student and admin | JSON test cases | JSON
| What will you work on today? | Non working day | PM Review Preparation, debug, deployment and update bug metrics, schedule | PM Review | Add session authentication to student and admin | Start coding JSON test cases | NIL | NIL
| Do you have any obstacles? | No issues | No issues | Amazon reads csv files differently from how our local machine reads it | Have to add Iteration 5 to our plan, so existing schedule has to be changed | NIL | The working of JSON took some time to understand | JSON test case implementation took time to understand

## Week 8
Person | Question | Week: 7 October 2019 to 13 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non working day | NIL | Group meeting, allocation of tasks, start manual testing for round 1 | Manual testing for round 1 and round 2 | Finish round 2 testing | Non working day | Non working day
| What will you do today? | NIL | Group meeting to discuss round 2 code and understanding JSON test cases | Manual testing for round 1 & 2 | Finish round 2 testing | NIL | Non working day | Non working day (overseas)
| Do you have any obstacles? | NIL | NIL | Yes, we found errors while performing testing and took time to figure out thesolution as we were not the ones who had written the code for that | Yes, we came through some errors in the code | Nope | NIL | NIL
Rou Hui | What did you do yesterday? | Non working day | Code Round 2 Clearing Logic and View Round 2 Results | Team meeting - knowledge sharing and test case discussion + changed bidding_round table structure and integrate code | Create tables to store unsuccessful bids and integrate code | Finish round 2 testing | Non working day | Non working day
| What will you work on today? | Code Round 2 Clearing Logic and View Round 2 Results | Group meeting to discuss round 2 code and understanding JSON test cases | Create tables to store unsuccessful bids and integrate code | Manual testing for round 1 and round 2 | NIL | Non working day | Code start/stop JSON
| Do you have any obstacles? | NIL | NIL | Change in table structure affects many different pages | Yes, we came through some errors in the code | Nope | No | NIL
Brian | What did you do yesterday? | Non working day | Code Round 2 Clearing Logic and View Round 2 Results | Team meeting - knowledge sharing and test case discussion + changed bidding_round table structure and integrate code | Create tables to store unsuccessful bids and integrate code | Fix bugs found during manual testing | Work on JSON testing | Non working day
| What will you work on today? | Code Round 2 Clearing Logic and View Round 2 Results | Group meeting to discuss round 2 code and understanding JSON test cases | Create tables to store unsuccessful bids and integrate code | Fix bugs found during manual testing | Work on JSON testing | Non working day | Code start/stop JSON
| Do you have any obstacles? | NIL | NIL | Change in table structure affects many different pages | NIL | NIL | No | NIL
Ian | What did you do yesterday? | Round 2 live view | Integration | Group meeting, start making slides for week 9 review | Make schedule iteration 5 and continue working on slides for week 9 review | NIL | Help with JSON test cases | Non working day
| What will you work on today? | Work on integration | Group meeting to discuss round 2 code and understanding JSON test cases | Make schedule iteration 5 and continue working on slides for week 9 review | NIL | Help with JSON test cases | Non working day | Code JSON dump and JSON student bidding
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Gordon | What did you do yesterday? | Nil | JSON test cases | Meeting, discussed JSON test cases with everyone, told them how it works | continue working on JSON test cases | JSON test cases | Non working day | Non working day
| What will you work on today? | JSON test cases | Group meeting to discuss round 2 code and understanding JSON test cases | continue working on JSON test cases | JSOn test cases | NIL | Non working day | Code JSON dump and JSON student bidding
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 9
Person | Question | Week: 14 October 2019 to 20 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non working day (overseas) | Non working day | Deployment, meeting with team, prepare for review, finish testing | Online review + Iteration 3 planning meeting | Work on JSON test cases | JSON test cases | Integrate changes requested in online review (combined info in student home page) Code student timetable feature
| What will you do today? | Non working day | Deployment, meeting with team, prepare for review, finish testing | Online review preparations | Work on JSON test cases | Work on JSON test cases and manual testing | Integrate changes requested in online review (combined info in student home page) Code student timetable feature | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Rou Hui | What did you do yesterday? | Review and test JSON test cases | Continue reviewing and testing JSON test cases | Deployment, meeting with team, prepare for review, finish testing | Online review + Iteration 3 planning meeting | Work on JSON test cases | JSON test cases | Integrate changes requested in online review (combined info in student home page)
| What will you work on today? | Continue reviewing and testing JSON test cases | Deployment, meeting with team, prepare for review, finish testing | Online review preparations | Work on JSON test cases | Work on JSON test cases and manual testing | Integrate changes requested in online review (combined info in student home page) | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Brian | What did you do yesterday? | Review and test JSON test cases | Continue reviewing and testing JSON test cases | Deployment, meeting with team, prepare for review, finish testing | Online review + Iteration 3 planning meeting | Work on JSON test cases | Review JSON test cases | Code search bid
| What will you work on today? | Continue reviewing and testing JSON test cases | Deployment, meeting with team, prepare for review, finish testing | Online review preparations | Work on JSON test cases | Work on JSON test cases and manual testing | Code search bid | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ian | What did you do yesterday? | Review and test JSON test cases | Continue reviewing and testing JSON test cases | Deployment, meeting with team, prepare for review, finish testing | Online review + Iteration 3 planning meeting | Work on JSON test cases | Work on JSON test cases and manual testing | Code student timetable feature
| What will you work on today? | Continue reviewing and testing JSON test cases | Deployment, meeting with team, prepare for review, finish testing | Online review preparations | Work on JSON test cases | Work on JSON test cases and manual testing | Code student timetable feature | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Gordon | What did you do yesterday? | Review and test JSON test cases | Continue reviewing and testing JSON test cases | JSON testing | Online review + Iteration 3 planning meeting | Work on JSON test cases | Review JSON test cases | Code search bid
| What will you work on today? | Continue reviewing and testing JSON test cases | JSON testing | Online review preparations | Work on JSON test cases | Work on JSON test cases and manual testing | Code search bid | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 10
Person | Question | Week: 21 October 2019 to 27 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | Review test cases and conduct JSON testing | Code search bid | Code search bid, Debugging | JSON testing & debugging | Continue reviewing test cases | Non-working day
| What will you do today? | Review test cases and conduct JSON testing | Code search bid | Continue code search bid, Debugging | JSON testing & debugging | Continue reviewing test cases | Non-working day | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Rou Hui | What did you do yesterday? | Non-working day | Review test cases and conduct JSON testing | Continue JSON testing | Continue test cases and JSON testing | Review test cases | Continue reviewing test cases | Non-working day
| What will you work on today? | Review test cases and conduct JSON testing | Continue JSON testing | Continue test cases and JSON testing | Review test cases | Continue reviewing test cases | Non-working day | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Brian | What did you do yesterday? | Non-working day | Review test cases and conduct JSON testing | JSON testing | JSON testing | Review test cases | Continue reviewing test cases | Non-working day
| What will you work on today? | Review test cases and conduct JSON testing | Continue JSON testing | Continue JSON testing | Review test cases | Continue reviewing test cases | Non-working day | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ian | What did you do yesterday? | Non-working day | Review test cases and conduct JSON testing | JSON testing & Debug code | Test cases and JSON testing | Review test cases | Continue reviewing test cases | Non-working day
| What will you work on today? | Review test cases and conduct JSON testing | JSON testing & Debug code | Continue test cases and JSON testing | Review test cases | Continue reviewing test cases | Non-working day | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Gordon | What did you do yesterday? | Non-working day | Review test cases and conduct JSON testing | Code search bid | Code search bid, debugging | JSON testing & debugging | Continue reviewing test cases | Non-working day
| What will you work on today? | Review test cases and conduct JSON testing | Code search bid | Continue code search bid, debugging | JSON testing & debugging | Continue reviewing test cases | Non-working day | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 11
Person | Question | Week: 28 October 2019 to 3 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | Review test cases | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting and updated minor mistake on bootstap | Non-working day | Check for any bugs
| What will you do today? | Review test cases | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Non-working day | Check for any bugs | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Rou Hui | What did you do yesterday? | Non-working day | Review test cases | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Continue to review mistakes from UAT | Non-working day
| What will you work on today? | Review test cases | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Continue to review mistakes from UAT | Non-working day | Preparation of bug metric
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Brian | What did you do yesterday? | Non-working day | Review test cases | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Continue to review mistakes from UAT | Non-working day
| What will you work on today? | Review test cases | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Continue to review mistakes from UAT | Non-working day | Preparation of bug metric
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ian | What did you do yesterday? | Non-working day | JSON debugging | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Continue to review mistakes from UAT | Non-working day
| What will you work on today? | JSON debugging | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Continue to review mistakes from UAT | Non-working day | Preparation of bug metric
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Gordon | What did you do yesterday? | Non-working day | JSON debugging | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting and updated minor mistake on bootstap | Non-working day | Check for any bugs
| What will you work on today? | JSON debugging | Iteration 3 milestone preparation for UAT | in-class UAT | iteration 4 meeting | Non-working day | Check for any bugs | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 12
Person | Question | Week: 4 November 2019 to 10 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | fix bugs found from bug metric | Iteration 4 meeting, add bugs found from UAT to bug metric, debugging | Debug real-time results bug from UAT
| What will you do today? | fix bugs found from bug metric | Iteration 4 meeting, add bugs found from UAT to bug metric, debugging | Debug real-time results bug from UAT | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL
Rou Hui | What did you do yesterday? | Preparation of bug metric | Non-working day | Iteration 4 meeting and review updated bug metric | Review debugged functions and final presentation slides
| What will you work on today? | Non-working day | Iteration 4 meeting and review updated bug metric | Review debugged functions and final presentation slides | Prepare use of GIT
| Do you have any obstacles? | NIL | NIL | NIL | NIL
Brian | What did you do yesterday? | Preparation of bug metric | fix bugs found from bug metric | Iteration 4 meeting, add bugs found from UAT to bug metric, debugging | Debug real-time results bug from UAT
| What will you work on today? | fix bugs found from bug metric | Iteration 4 meeting, add bugs found from UAT to bug metric, debugging | Debug real-time results bug from UAT | Non-working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL
Ian | What did you do yesterday? | Preparation of bug metric | Non-working day | Iteration 4 meeting and review updated bug metric | Review debugged functions and final presentation slides
| What will you work on today? | Non-working day | Iteration 4 meeting and review updated bug metric | Review debugged functions and final presentation slides | Prepare use of GIT
| Do you have any obstacles? | NIL | NIL | NIL | NIL
Gordon | What did you do yesterday? | Non-working day | Review bug matric | Iteration 4 meeting and review updated bug metric | Review debugged functions and final presentation slides
| What will you work on today? | Review bug matric | Iteration 4 meeting and review updated bug metric | Review debugged functions and final presentation slides | Prepare use of GIT
| Do you have any obstacles? | NIL | NIL | NIL | NIL