## Week 6
Person | Question | Week: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day | Code connection manager and protect files
| What will you do today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files
| Do you have any obstacles? | NIL | Windows and Mac have different default SQL credentials so was stuck for awhile
Rou Hui | What did you do yesterday? | Non-working day | Code connection manager and protect files
| What will you work on today? | Start coding common files (eg. connection manager, protect) | Code common, JWT, token files
| Do you have any obstacles? | NIL | Windows and Mac have different default SQL credentials so was stuck for awhile
Brian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out
| What will you work on today? | Start coding DAOs | Code remaining DAOs
| Do you have any obstacles? | NIL | Integrating StudentDAO done by other pair with our version of StudentDAO
Ian | What did you do yesterday? | Non-working day | Updated StudentDAO, coded SectionDAO, CourseDAO, sign out
| What will you work on today? | Start coding DAOs | Code remaining DAOs
| Do you have any obstacles? | NIL | Integrating StudentDAO done by other pair with our version of StudentDAO
Gordon | What did you do yesterday? | Check forum, project wiki and update requirements and finalize schedule | Non-working day
| What will you work on today? | Non-working day | PM Review preparation for week 7
| Do you have any obstacles? | NIL | NIL