## Week 6
Person | Question | Week: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Amey | What did you do yesterday? | Non-working day
| What will you do today? | Start coding common files (eg. connection manager, protect)
| Do you have any obstacles? | NIL
Rou Hui | What did you do yesterday? | Non-working day
| What will you work on today? | Start coding common files (eg. connection manager, protect)
| Do you have any obstacles? | NIL
Brian | What did you do yesterday? | Non-working day
| What will you work on today? | Start coding DAOs
| Do you have any obstacles? | NIL
Ian | What did you do yesterday? | Non-working day
| What will you work on today? | Start coding DAOs
| Do you have any obstacles? | NIL
Gordon | What did you do yesterday? | Check forum, project wiki and update requirements and finalize schedule
| What will you work on today? | Non-working day
| Do you have any obstacles? | NIL