## Schedule
Iteration No | Task ID | DESCRIPTION | TYPE | PLANNED DATETIME START | PLANNED DATETIME END | HOURS SPENT PLANNED | ACTUAL DATETIME START | ACTUAL DATETIME END | HOURS SPENT ACTUAL | STATUS | Is Critical Path | Not planned | Predecessor | LOCATION | FINAL COMMIT ID | PP PHOTO LINK | AR | BG | GL | IL | RH | Est Days | Act Days | Planned Prog Hrs | Prog Hrs | Non-Prog Hrs | ItrStatus | ItrNot planned
1 | 1 | Iteration 1: Planning | Team Meeting - Planning, Admin, & Updates | 2019-09-18 12:00 | 2019-09-18 15:00 | 3 | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | Completed |  | No |  | LKS PR 2.3
1 | 1_1 | Plan project schedule and Iteration 1 | Team Meeting - Planning, Admin, & Updates | 2019-09-18 12:00 | 2019-09-18 15:00 | 3 | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | Completed | Yes | No |  | LKS PR 2.3 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee | 0.125 | 0.125 | 0 | 0 | 3 | 1Completed | 1No
1 | 1_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-09-18 12:00 | 2019-09-18 15:00 | 3 | 2019-09-19 12:00 | 2019-09-19 15:00 | 3 | Completed | No | No |  | LKS PR 2.3 | 7f061a71a453c5f30ebcf511c74e3fbba187656a |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 2 | Design database structure | Design - Other | 2019-09-20 12:00 | 2019-09-20 14:00 | 2 | 2019-09-19 15:30 | 2019-09-19 19:00 | 3.5 | Completed | Yes | No | 1_1_1 | SIS Subway |  |  |  | Attendee |  | Attendee |  | 0.083333 | 0.14583 | 0 | 0 | 3.5 | 1Completed | 1No
1 | 3 | Code student login process | Programming - Features | 2019-09-20 09:00 | 2019-09-20 12:00 | 3 | 2019-09-20 09:00 | 2019-09-20 15:00 | 3 | Completed |  | No
1 | 3_1 | Code StudentDAO | Programming - Features | 2019-09-20 09:00 | 2019-09-20 10:00 | 1 | 2019-09-20 09:00 | 2019-09-20 11:00 | 2 | Completed | No | No | 1_2 | SIS L3 Benches | 04ee823dd7f4267738e512dd8f88072c5cd2f899 |  | Attendee |  |  |  | Attendee | 0.041667 | 0.083333 | 1 | 2 | 0 | 1Completed | 1No
1 | 3_2 | Code login interface | Programming - Features | 2019-09-20 10:00 | 2019-09-20 10:30 | 0.5 | 2019-09-20 11:00 | 2019-09-20 11:30 | 0.5 | Completed | No | No | 1_2 |  |  |  | Attendee |  |  |  | Attendee
1 | 3_3 | Code connection manager | Programming - Features | 2019-09-20 10:30 | 2019-09-20 11:00 | 0.5 | 2019-09-20 11:30 | 2019-09-20 12:00 | 0.5 | Completed | Yes | No | 1_2 |  | b6aec58bd6a5fc45343f4e26b865a9783ee873b3 |  | Attendee |  |  |  | Attendee
1 | 3_4 | Code login authentication | Programming - Features | 2019-09-20 11:00 | 2019-09-20 12:00 | 1 | 2019-09-20 12:00 | 2019-09-20 15:00 | 3 | Completed | No | No | 1_2 |  | 6d144fa99ad9f8e87077842d06d311ea0b4f0250 |  | Attendee |  |  |  | Attendee
1 | 4 | Basic CSS design | Design - Other | 2019-09-20 15:00 | 2019-09-20 17:00 | 2 | 2019-09-20 12:00 | 2019-09-20 13:30 | 1.5 | Completed | No | No | 1_1_1 |  | 7cd160145a2bdb90565dcfb242172dc8584e8ca5 |  |  | Attendee |  | Attendee |  | 0.083333 | 0.0625 | 0 | 0 | 1.5 | 1Completed | 1No
1 | 5 | Code remaining DAOs | Programming - Features | 2019-09-21 11:00 | 2019-09-22 15:00 | 4 | 2019-09-23 16:00 | 2019-09-25 13:00 | 7 | Completed | Yes | No | 1_2, 1_3_3 |  | affb095381259000a57710e12e94944fafaac2a0 |  |  | Attendee |  | Attendee |  | 1.1667 | 1.875 | 4 | 7 | 0 | 1Completed | 1No
1 | 6 | Code remaining common files | Programming - Features | 2019-09-23 09:00 | 2019-09-23 11:00 | 2 | 2019-09-23 17:00 | 2019-09-24 19:00 | 4 | Completed | No | No | 1_1_1 |  | 9ca90a3375d13a6ec879348def9b9d6c3accf7b4 |  | Attendee |  |  |  | Attendee | 0.083333 | 1.0833 | 2 | 4 | 0 | 1Completed | 1No
1 | 7 | Code bootstrap | Programming - Features | 2019-09-23 16:00 | 2019-09-24 09:00 | 6 | 2019-09-24 16:00 | 2019-09-26 17:00 | 7 | Completed | Yes | No | 1_5 |  | e4e0b8b1590e8efab4eec6d1fd4435be30bd6ea2 |  |  | Attendee |  | Attendee |  | 0.70833 | 2.0417 | 6 | 7 | 0 | 1Completed | 1No
1 | 8 | Integrate Code | Programming - Integration | 2019-09-26 09:00 | 2019-09-26 12:00 | 3 | 2019-09-27 12:00 | 2019-09-27 18:00 | 5 | Completed | Yes | No | 1_3_1, 1_3_2, 1_3_3, 1_3_4, 1_4, 1_6, 1_7 |  |  |  | Attendee |  |  |  | Attendee | 0.125 | 0.25 | 3 | 5 | 0 | 1Completed | 1No
1 | 9 | Test Code | Testing - Integration (local) | 2019-09-26 13:00 | 2019-09-27 09:30 | 3 | 2019-09-27 15:00 | 2019-09-28 18:00 | 5 | Completed |  | No
1 | 9_1 | Create test cases | Testing - Updating Test Log / Test Cases | 2019-09-26 13:00 | 2019-09-26 14:30 | 1.5 | 2019-09-27 15:00 | 2019-09-27 17:00 | 2 | Completed | Yes | No |  |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 9_2 | Update bug log and bug metrics | Testing - Integration (local) | 2019-09-27 08:00 | 2019-09-27 09:30 | 1.5 | 2019-09-27 17:00 | 2019-09-28 16:00 | 3 | Incomplete | Yes | No |  |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 10 | Debug code | Programming - Debugging | 2019-09-27 12:00 | 2019-09-27 14:00 | 2 | 2019-09-29 13:00 | 2019-10-01 14:00 | 4 | Incomplete | Yes | No | 1_9_1, 1_9_2 |  | e92a1dd488baca41e1b2bdfce5cc7de8f6a3260e |  |  | Attendee |  | Attendee
1 | 11 | Deploy to AWS | Deployment | 2019-09-27 17:00 | 2019-09-27 18:00 | 1 | 2019-10-01 16:00 | 2019-10-01 18:00 | 2 | Completed | Yes | No | 1_10 |  |  |  |  | Attendee |  | Attendee |  | 0.041667 | 0.083333 | 0 | 0 | 2 | 1Completed | 1No
1 | 12 | Iteration 1: Review | Team Meeting - Planning, Admin, & Updates | 2019-09-28 08:30 | 2019-09-28 10:30 | 2 | 2019-09-28 10:30 | 2019-09-28 13:30 | 3 | Completed |  | No |  | SOE / SOSS GSR 3-12
1 | 12_1 | Plan Round 1 | Team Meeting - Planning, Admin, & Updates | 2019-09-28 08:30 | 2019-09-28 10:30 | 2 | 2019-09-28 10:30 | 2019-09-28 13:30 | 3 | Completed | No | No | 1_11 | SOE / SOSS GSR 3-12 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 12_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-09-28 08:30 | 2019-09-28 10:30 | 2 | 2019-09-28 10:30 | 2019-09-28 13:30 | 3 | Completed | No | No |  | SOE / SOSS GSR 3-12 | 07b8379ca40832dc3d80123cf854a626598a9088 |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 13 | Student Bidding | Programming - Features | 2019-09-28 11:00 | 2019-09-28 15:00 | 4 | 2019-09-29 15:00 | 2019-09-29 19:00 | 4 | Completed |  | No
1 | 13_1 | Round 1: Add bid | Programming - Features | 2019-09-28 11:00 | 2019-09-28 13:00 | 2 | 2019-09-30 07:30 | 2019-09-30 09:00 | 1.5 | Completed | No | No | 1_12_1 |  | d23012857716870472ebbca7cb696c2f63c1b193 |  | Attendee |  |  |  | Attendee | 0.083333 | 0.0625 | 2 | 1.5 | 0 | 1Completed | 1No
1 | 13_2 | Round 1: View bid | Programming - Features | 2019-09-28 11:00 | 2019-09-28 13:00 | 2 | 2019-09-29 16:30 | 2019-09-29 18:30 | 2 | Completed | No | No | 1_12_1 |  | dd438f0eae2933e7491fbe719b02ede0ccb50b63 |  |  | Attendee |  | Attendee |  | 0.083333 | 0.083333 | 2 | 2 | 0 | 1Completed | 1No
1 | 13_3 | Round 1: Drop bid | Programming - Features | 2019-09-28 13:00 | 2019-09-28 15:00 | 2 | 2019-09-30 09:00 | 2019-09-30 10:00 | 1 | Completed | No | No | 1_12_1 |  | d23012857716870472ebbca7cb696c2f63c1b193 |  | Attendee |  |  |  | Attendee | 0.083333 | 0.041667 | 2 | 1 | 0 | 1Completed | 1No
1 | 14 | Round 1: Admin Clearing Logic | Programming - Features | 2019-09-29 14:00 | 2019-09-30 12:00 | 4 | 2019-09-30 10:00 | 2019-10-01 13:30 | 3 | Completed | No | No | 1_12_1 |  |  |  |  | Attendee |  | Attendee |  | 0.91667 | 1.1458 | 4 | 3 | 0 | 1Completed | 1No
1 | 15 | Iteration 1: Milestone Preparation | Milestone - Preparation | 2019-09-30 12:00 | 2019-10-02 11:00 | 8 | 2019-10-01 12:00 | 2019-10-01 20:00 | 8 | Completed |  | No |  | Project Way |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 15_1 | PM Review Preparation | Milestone - Preparation | 2019-09-30 12:00 | 2019-10-02 11:00 | 8 | 2019-10-01 12:00 | 2019-10-01 20:00 | 8 | Completed | Yes | No | 1_11 | Project Way |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 15_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-09-30 12:00 | 2019-10-02 11:00 | 8 | 2019-10-01 12:00 | 2019-10-01 20:00 | 8 | Completed | No | No |  | Project Way |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 16 | PM Review | Milestone - Presentations | 2019-10-02 15:15 | 2019-10-02 16:15 | 1 | 2019-10-02 15:15 | 2019-10-02 16:15 | 1 | Not started | Yes | No | 1_15_1 | SIS SR 3-1 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
1 | 17 | Daily Update 1 | Project Management - Update Schedule | 2019-09-21 11:00 | 2019-09-21 12:00 | 1 | 2019-09-21 11:00 | 2019-09-21 12:00 | 1 | Completed | No | No |  |  | ad115ffdf100c4d8c4d96032fdebc86e1c7918c0 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 18 | Daily Update 2 | Project Management - Update Schedule | 2019-09-22 11:00 | 2019-09-22 12:00 | 1 | 2019-09-22 11:00 | 2019-09-22 12:00 | 1 | Completed | No | No |  |  | 12699e890f5639e1f32e720893ff1630c1976b4d |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 19 | Daily Update 3 | Project Management - Update Schedule | 2019-09-23 11:00 | 2019-09-23 12:00 | 1 | 2019-09-23 11:00 | 2019-09-23 12:00 | 1 | Completed | No | No |  |  | d5da75da64ef5c62716e1b5e102f26f8b4182fca |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 20 | Daily Update 4 | Project Management - Update Schedule | 2019-09-24 11:00 | 2019-09-24 12:00 | 1 | 2019-09-24 11:00 | 2019-09-24 12:00 | 1 | Completed | No | No |  |  | c0f96eb88ad36a957a1b16ba59d700e65ea50ff7 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 21 | Daily Update 5 | Project Management - Update Schedule | 2019-09-25 11:00 | 2019-09-25 12:00 | 1 | 2019-09-25 11:00 | 2019-09-25 12:00 | 1 | Completed | No | No |  |  | bb51027ecd46cd44716e26abc550dc4826f3361d |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 22 | Daily Update 6 | Project Management - Update Schedule | 2019-09-26 11:00 | 2019-09-26 12:00 | 1 | 2019-09-26 11:00 | 2019-09-26 12:00 | 1 | Completed | No | No |  |  | 5f680fc98e365a930440fda304e1678053bbddd7 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 23 | Daily Update 7 | Project Management - Update Schedule | 2019-09-27 11:00 | 2019-09-27 12:00 | 1 | 2019-09-27 11:00 | 2019-09-27 12:00 | 1 | Completed | No | No |  |  | 8775506564206858f826688da73a9c22fa985f55 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 24 | Daily Update 8 | Project Management - Update Schedule | 2019-09-28 11:00 | 2019-09-28 12:00 | 1 | 2019-09-28 11:00 | 2019-09-28 12:00 | 1 | Completed | No | No |  |  | f855c859eb64c2ef59be724bd271c8e3e95d17d9 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 25 | Daily Update 9 | Project Management - Update Schedule | 2019-09-29 11:00 | 2019-09-29 12:00 | 1 | 2019-09-29 11:00 | 2019-09-29 12:00 | 1 | Completed | No | No |  |  | 8652b85a78da4f1cd1d84a7b1735f2a73c7ded85 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 26 | Daily Update 10 | Project Management - Update Schedule | 2019-09-30 11:00 | 2019-09-30 12:00 | 1 | 2019-09-30 11:00 | 2019-09-30 12:00 | 1 | Completed | No | No |  |  | 58826ed474080f1ea950375b566b20352cf397b3 |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 27 | Daily Update 11 | Project Management - Update Schedule | 2019-10-01 11:00 | 2019-10-01 12:00 | 1 | 2019-10-01 11:00 | 2019-10-01 12:00 | 1 | Not started | No | No |  |  |  |  | Attendee | Attendee | Attendee | Leader | Attendee
1 | 28 | Daily Update 12 | Project Management - Update Schedule | 2019-10-02 11:00 | 2019-10-02 12:00 | 1 | 2019-10-02 11:00 | 2019-10-02 12:00 | 1 | Not started | No | No |  |  |  |  | Attendee | Attendee | Attendee | Leader | Attendee
2 | 1 | Iteration 2: Planning | Team Meeting - Planning, Admin, & Updates | 2019-10-03 12:00 | 2019-10-03 15:00 | 3 |  |  |  | Not started |  | No
2 | 1_1 | Plan tasks allocation and schedule | Team Meeting - Planning, Admin, & Updates | 2019-10-03 12:00 | 2019-10-03 15:00 | 3 |  |  |  | Not started | Yes | No |  |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 1_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-03 12:00 | 2019-10-03 15:00 | 3 |  |  |  | Not started | No | No |  |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 2 | Code Round 2 | Programming - Features | 2019-10-04 09:00 | 2019-10-07 18:00 |  |  |  |  | Not started |  | No
2 | 2_1 | View Round 1 Results | Programming - Features | 2019-10-04 09:00 | 2019-10-04 12:00 | 3 |  |  |  | Not started | No | No | 2_1 | [5 empty] | Attendee | Attendee |  | 0.125 | 0 | 3 | 0 | 0 | 2Not started | 2No
2 | 2_2 | Round 2: View Real Time Bids | Programming - Features | 2019-10-05 09:00 | 2019-10-07 18:00 | 10 |  |  |  | Not started | Yes | No | 2_1 | [5 empty] | Attendee | Attendee |  | 2.375 | 0 | 10 | 0 | 0 | 2Not started | 2No
2 | 2_3 | Round 2: Admin Clearing Logic | Programming - Features | 2019-10-04 09:00 | 2019-10-05 15:00 | 8 |  |  |  | Not started | Yes | No | 2_1 |  |  |  |  | Attendee |  |  | Attendee | 1.25 | 0 | 8 | 0 | 0 | 2Not started | 2No
2 | 2_4 | View Round 2 Results | Programming - Features | 2019-10-07 13:00 | 2019-10-07 16:00 | 3 |  |  |  | Not started | Yes | No | 2_2_3 |  |  |  |  | Attendee |  |  | Attendee | 0.125 | 0 | 3 | 0 | 0 | 2Not started | 2No
2 | 3 | Integrate Code | Programming - Integration | 2019-10-08 11:00 | 2019-10-08 13:00 | 2 |  |  |  | Not started | Yes | No | 2_2_1, 2_2_2, 2_2_3 | [5 empty] | Attendee | Attendee
2 | 4 | Test Code | Testing - Integration (local) | 2019-10-09 10:00 | 2019-10-11 14:00 |  |  |  |  | Not started |  | No
2 | 4_1 | Create test cases | Testing - Updating Test Log / Test Cases | 2019-10-09 10:00 | 2019-10-09 12:00 | 2 |  |  |  | Not started | Yes | No | 2_3 |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 4_2 | Code JSON authentication and update bug log | Programming - Debugging | 2019-10-09 13:00 | 2019-10-11 10:00 | 10 |  |  |  | Not started | Yes | No | 2_4_1 | [5 empty] | Attendee | Attendee
2 | 4_3 | Update bug metrics | Testing - Integration (local) | 2019-10-11 12:00 | 2019-10-11 14:00 | 2 |  |  |  | Not started | Yes | No | 2_4_2 |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 5 | Debug code | Programming - Debugging | 2019-10-12 10:00 | 2019-10-12 13:00 | 3 |  |  |  | Not started | Yes | No | 2_4_3 |  |  |  |  | Attendee |  |  | Attendee
2 | 6 | Deploy code to AWS | Deployment | 2019-10-13 16:00 | 2019-10-13 18:00 | 2 |  |  |  | Not started | Yes | No | 2_5 | [5 empty] | Attendee | Attendee
2 | 7 | Iteration 2: Milestone Preparation | Milestone - Preparation | 2019-10-14 12:00 | 2019-10-14 15:00 | 3 |  |  |  | Not started |  | No
2 | 7_1 | Online Review Preparation | Milestone - Preparation | 2019-10-14 12:00 | 2019-10-14 15:00 | 3 |  |  |  | Not started | Yes | No | 2_6 |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 7_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-14 12:00 | 2019-10-14 15:00 | 3 |  |  |  | Not started | No | No |  |  |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 8 | Online Review | Milestone - Presentations | 2019-10-16 15:15 | 2019-10-16 18:45 | 1 |  |  |  | Not started | Yes | No | 2_7_1 | SIS SR 3-1 |  |  | Attendee | Attendee | Attendee | Attendee | Attendee
2 | 9 | Daily Update 1 | Project Management - Update Schedule | 2019-10-03 11:00 | 2019-10-03 12:00 | 1 | 2019-10-03 11:00 | 2019-10-03 12:00 | 1 | Not started | No | No
2 | 10 | Daily Update 2 | Project Management - Update Schedule | 2019-10-04 11:00 | 2019-10-04 12:00 | 1 | 2019-10-04 11:00 | 2019-10-04 12:00 | 1 | Not started | No | No
2 | 11 | Daily Update 3 | Project Management - Update Schedule | 2019-10-05 11:00 | 2019-10-05 12:00 | 1 | 2019-10-05 11:00 | 2019-10-05 12:00 | 1 | Not started | No | No
2 | 12 | Daily Update 4 | Project Management - Update Schedule | 2019-10-06 11:00 | 2019-10-06 12:00 | 1 | 2019-10-06 11:00 | 2019-10-06 12:00 | 1 | Not started | No | No
2 | 13 | Daily Update 5 | Project Management - Update Schedule | 2019-10-07 11:00 | 2019-10-07 12:00 | 1 | 2019-10-07 11:00 | 2019-10-07 12:00 | 1 | Not started | No | No
2 | 14 | Daily Update 6 | Project Management - Update Schedule | 2019-10-08 11:00 | 2019-10-08 12:00 | 1 | 2019-10-08 11:00 | 2019-10-08 12:00 | 1 | Not started | No | No
2 | 15 | Daily Update 7 | Project Management - Update Schedule | 2019-10-09 11:00 | 2019-10-09 12:00 | 1 | 2019-10-09 11:00 | 2019-10-09 12:00 | 1 | Not started | No | No
2 | 16 | Daily Update 8 | Project Management - Update Schedule | 2019-10-10 11:00 | 2019-10-10 12:00 | 1 | 2019-10-10 11:00 | 2019-10-10 12:00 | 1 | Not started | No | No
2 | 17 | Daily Update 9 | Project Management - Update Schedule | 2019-10-11 11:00 | 2019-10-11 12:00 | 1 | 2019-10-11 11:00 | 2019-10-11 12:00 | 1 | Not started | No | No
2 | 18 | Daily Update 10 | Project Management - Update Schedule | 2019-10-12 11:00 | 2019-10-12 12:00 | 1 | 2019-10-12 11:00 | 2019-10-12 12:00 | 1 | Not started | No | No
2 | 19 | Daily Update 11 | Project Management - Update Schedule | 2019-10-13 11:00 | 2019-10-13 12:00 | 1 | 2019-10-13 11:00 | 2019-10-13 12:00 | 1 | Not started | No | No
2 | 20 | Daily Update 12 | Project Management - Update Schedule | 2019-10-14 11:00 | 2019-10-14 12:00 | 1 | 2019-10-14 11:00 | 2019-10-14 12:00 | 1 | Not started | No | No
2 | 21 | Daily Update 13 | Project Management - Update Schedule | 2019-10-15 11:00 | 2019-10-15 12:00 | 1 | 2019-10-15 11:00 | 2019-10-15 12:00 | 1 | Not started | No | No
2 | 22 | Daily Update 14 | Project Management - Update Schedule | 2019-10-16 11:00 | 2019-10-16 12:00 | 1 | 2019-10-16 11:00 | 2019-10-16 12:00 | 1 | Not started | No | No
3 | 1 | Iteration 3: Planning | Team Meeting - Planning, Admin, & Updates | 2019-10-17 10:00 | 2019-10-17 12:00 | 2 |  |  |  | Not started |  | No
3 | 1_1 | Plan tasks allocation and schedule | Team Meeting - Planning, Admin, & Updates | 2019-10-17 10:00 | 2019-10-17 12:00 | 2 |  |  |  | Not started | Yes | No
3 | 1_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-17 10:00 | 2019-10-17 12:00 | 2 |  |  |  | Not started | No | No
3 | 2 | Code timetable | Programming - Features | 2019-10-17 12:00 | 2019-10-19 13:00 | 10 |  |  |  | Not started | Yes | No | 3_1
3 | 3 | Code search bid | Programming - Features | 2019-10-17 12:00 | 2019-10-19 13:00 | 10 |  |  |  | Not started | Yes | No | 3_1
3 | 4 | Integrate Code | Programming - Integration | 2019-10-20 13:00 | 2019-10-20 16:00 | 3 |  |  |  | Not started | Yes | No | 3_2, 3_3
3 | 5 | Test Code | Testing - Integration (local) | [6 empty] | Not started |  | No
3 | 5_1 | Create test cases | Testing - Updating Test Log / Test Cases | 2019-10-21 15:30 | 2019-10-21 17:30 | 2 |  |  |  | Not started | Yes | No | 3_4
3 | 5_2 | Update bug log and bug metrics | Testing - Integration (local) | 2019-10-22 12:00 | 2019-10-22 15:00 | 3 |  |  |  | Not started | Yes | No | 3_5_1
3 | 6 | Debug code | Programming - Debugging | 2019-10-23 08:00 | 2019-10-24 12:00 | 8 |  |  |  | Not started | Yes | No | 3_5_2
3 | 7 | Deploy code to AWS | Deployment | 2019-10-25 14:00 | 2019-10-25 15:00 | 1 |  |  |  | Not started | Yes | No | 3_6, 3_10
3 | 8 | Iteration 3: Milestone Preparation | Milestone - Preparation | 2019-10-26 12:00 | 2019-10-26 15:00 | 3 |  |  |  | Not started |  | No
3 | 8_1 | UAT Preparation | Milestone - Preparation | 2019-10-26 12:00 | 2019-10-26 15:00 | 3 |  |  |  | Not started | Yes | No | 3_7
3 | 8_2 | Meeting Minutes | Team Meeting - Update Minutes | 2019-10-26 12:00 | 2019-10-26 15:00 | 3 |  |  |  | Not started | No | No
3 | 9 | UAT | Milestone - Presentations | 2019-10-30 15:15 | 2019-10-30 18:45 | 1 |  |  |  | Not started | Yes | No | 3_8_1 | SIS SR 3-1
3 | 10 | UI Design | Design - Other | 2019-10-27 12:00 | 2019-10-29 18:00 | 6 |  |  |  | Not started | No | No | 3_1
3 | 11 | Daily Update 1 | Project Management - Update Schedule | 2019-10-17 11:00 | 2019-10-17 12:00 | 1 | 2019-10-17 11:00 | 2019-10-17 12:00 | 1 | Not started | No | No
3 | 12 | Daily Update 2 | Project Management - Update Schedule | 2019-10-18 11:00 | 2019-10-18 12:00 | 1 | 2019-10-18 11:00 | 2019-10-18 12:00 | 1 | Not started | No | No
3 | 13 | Daily Update 3 | Project Management - Update Schedule | 2019-10-19 11:00 | 2019-10-19 12:00 | 1 | 2019-10-19 11:00 | 2019-10-19 12:00 | 1 | Not started | No | No
3 | 14 | Daily Update 4 | Project Management - Update Schedule | 2019-10-20 11:00 | 2019-10-20 12:00 | 1 | 2019-10-20 11:00 | 2019-10-20 12:00 | 1 | Not started | No | No
3 | 15 | Daily Update 5 | Project Management - Update Schedule | 2019-10-21 11:00 | 2019-10-21 12:00 | 1 | 2019-10-21 11:00 | 2019-10-21 12:00 | 1 | Not started | No | No
3 | 16 | Daily Update 6 | Project Management - Update Schedule | 2019-10-22 11:00 | 2019-10-22 12:00 | 1 | 2019-10-22 11:00 | 2019-10-22 12:00 | 1 | Not started | No | No
3 | 17 | Daily Update 7 | Project Management - Update Schedule | 2019-10-23 11:00 | 2019-10-23 12:00 | 1 | 2019-10-23 11:00 | 2019-10-23 12:00 | 1 | Not started | No | No
3 | 18 | Daily Update 8 | Project Management - Update Schedule | 2019-10-24 11:00 | 2019-10-24 12:00 | 1 | 2019-10-24 11:00 | 2019-10-24 12:00 | 1 | Not started | No | No
3 | 19 | Daily Update 9 | Project Management - Update Schedule | 2019-10-25 11:00 | 2019-10-25 12:00 | 1 | 2019-10-25 11:00 | 2019-10-25 12:00 | 1 | Not started | No | No
3 | 20 | Daily Update 10 | Project Management - Update Schedule | 2019-10-26 11:00 | 2019-10-26 12:00 | 1 | 2019-10-26 11:00 | 2019-10-26 12:00 | 1 | Not started | No | No
3 | 21 | Daily Update 11 | Project Management - Update Schedule | 2019-10-27 11:00 | 2019-10-27 12:00 | 1 | 2019-10-27 11:00 | 2019-10-27 12:00 | 1 | Not started | No | No
3 | 22 | Daily Update 12 | Project Management - Update Schedule | 2019-10-28 11:00 | 2019-10-28 12:00 | 1 | 2019-10-28 11:00 | 2019-10-28 12:00 | 1 | Not started | No | No
3 | 23 | Daily Update 13 | Project Management - Update Schedule | 2019-10-29 11:00 | 2019-10-29 12:00 | 1 | 2019-10-29 11:00 | 2019-10-29 12:00 | 1 | Not started | No | No
3 | 24 | Daily Update 14 | Project Management - Update Schedule | 2019-10-30 11:00 | 2019-10-30 12:00 | 1 | 2019-10-30 11:00 | 2019-10-30 12:00 | 1 | Not started | No | No
4 | 1 | Final Presentation Preparation | Milestone - Preparation | 2019-11-07 12:00 | 2019-11-17 12:00 | 24 |  |  |  | Not started | No | No
4 | 1_1 | Preparation - Schedule | Milestone - Preparation | 2019-11-07 12:00 | 2019-11-09 12:00 | 6 |  |  |  | Not started | Yes | No
4 | 1_2 | Preparation - Bug Metric | Milestone - Preparation | 2019-11-10 12:00 | 2019-11-12 12:00 | 6 |  |  |  | Not started | Yes | No | 4_1_1
4 | 1_3 | Preparation - Use of GIT | Milestone - Preparation | 2019-11-13 12:00 | 2019-11-15 12:00 | 6 |  |  |  | Not started | Yes | No | 4_1_2
4 | 1_4 | Preparation - Others | Milestone - Preparation | 2019-11-16 12:00 | 2019-11-18 12:00 | 6 |  |  |  | Not started | Yes | No | 4_1_3
4 | 1_5 | Meeting Minutes | Team Meeting - Update Minutes | 2019-11-07 12:00 | 2019-11-17 12:00 | 4 |  |  |  | Not started | No | No | 4_1_4
4 | 2 | Final Presentation | Milestone - Presentations | 2019-11-20 15:30 | 2019-11-20 18:45 | 1 |  |  |  | Not started | Yes | No | 4_1_5 | SIS SR 3-1
4 | 3 | Daily Update 1 | Project Management - Update Schedule | 2019-11-07 11:00 | 2019-11-07 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 4 | Daily Update 2 | Project Management - Update Schedule | 2019-11-08 11:00 | 2019-11-08 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 5 | Daily Update 3 | Project Management - Update Schedule | 2019-11-09 11:00 | 2019-11-09 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 6 | Daily Update 4 | Project Management - Update Schedule | 2019-11-10 11:00 | 2019-11-10 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 7 | Daily Update 5 | Project Management - Update Schedule | 2019-11-11 11:00 | 2019-11-11 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 8 | Daily Update 6 | Project Management - Update Schedule | 2019-11-12 11:00 | 2019-11-12 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 9 | Daily Update 7 | Project Management - Update Schedule | 2019-11-13 11:00 | 2019-11-13 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 10 | Daily Update 8 | Project Management - Update Schedule | 2019-11-14 11:00 | 2019-11-14 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 11 | Daily Update 9 | Project Management - Update Schedule | 2019-11-15 11:00 | 2019-11-15 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 12 | Daily Update 10 | Project Management - Update Schedule | 2019-11-16 11:00 | 2019-11-16 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 13 | Daily Update 11 | Project Management - Update Schedule | 2019-11-17 11:00 | 2019-11-17 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 14 | Daily Update 12 | Project Management - Update Schedule | 2019-11-18 11:00 | 2019-11-18 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 15 | Daily Update 13 | Project Management - Update Schedule | 2019-11-19 11:00 | 2019-11-19 12:00 | 1 |  |  | 1 | Not started | No | No
4 | 16 | Daily Update 14 | Project Management - Update Schedule | 2019-11-20 11:00 | 2019-11-20 12:00 | 1 |  |  | 1 | Not started | No | No
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0
Formulas:
Prog Hrs = IF(ISERROR(FIND("Programming",[TYPE])),0,[HOURS SPENT ACTUAL])
Non-Prog Hrs = [HOURS SPENT ACTUAL]-[Prog Hrs]
Note on M1: Enter "Yes" if task added in after iteration has started.
Note on P1: For any upload to Git
Note on Q1: For programming tasks only
Note on R1: Use initials
Note on S1: Use initials
Note on T1: Use initials
Note on U1: Use initials
Note on V1: Use initials
Note on C13: (common, protect, token, JWT) -BRIAN GOH JUN WEI

## Metrics
Burndown
Iteration No. | Planned | Actual
0 | 318 | 318
1 | 218 | 198.5
2 | 140 | 184.5
3 | 67 | 170.5
4 | 0 | 156.5
5 | 0 | 156.5
6 | 0 | 156.5
7 | 0 | 156.5
Task Completion Check
§Actual tasks / Estimated tasks completed
Iteration No. | Planned Tasks | Completed Tasks | Value
1 | 43 | 13 | 0.30233
2 | 33 | 0 | 0
3 | 30 | 0 | 0
4 | 21 | 0 | 0
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0!
7 | 0 | 0 | #DIV/0!
Iteration Completion Check
§Estimated time / actual time
Iteration No. | Estimated time | Actual Time | Value
1 | 3.625 | 7.0833 | 0.51176
2 | 3.875 | 0 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | 0 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0!
7 | 0 | 0 | #DIV/0!
Load factor
Hours/Day | planned and actual per iteration
Iteration No. | Planned Hrs | Actual Hrs
1 | 27.5862 | 16.8706
2 | 20.129 | #DIV/0!
3 | #DIV/0! | #DIV/0!
4 | #DIV/0! | #DIV/0!
5 | #DIV/0! | #DIV/0!
6 | #DIV/0! | #DIV/0!
7 | #DIV/0! | #DIV/0!
Hours spent per member
| AR | BG | GL | IL | RH | #REF!
Prog Hrs | 13.5 | 19 | 0 | 19 | 13.5 | #REF!
Non-prog Hrs | 3 | 10 | 3 | 10 | 3 | #REF!
Pair programming time check
Estimated PP hours/actual PP hours (per task)
0.5
0.57143
0.5
1.3333
1
2
1.3333

## Support
Raise any problems or questions in the eLearn Discussion Forum

## Config
Leader
Attendee
Programming - Features
Programming - Debugging
Programming - Integration
Deployment
Testing - Integration (local)
Testing - Deployment (cloud)
Testing - Updating Test Log / Test Cases
Team Meeting - Planning, Admin, & Updates
Team Meeting - Knowledge Sharing
Team Meeting - Update Minutes
Team Meeting - Other
Project Management - Update Schedule
Project Management - Update Metrics
Project Management - Other
Design - App Architecture (SD etc)
Design - Use Cases
Design - Other
Milestone - Preparation
Milestone - Presentations
Other
Yes
No
Not started
Started
Completed
Incomplete
Hold